## Sheet1
STATE DEPARTMENT FOR HOUSING AND URBAN DEVELOPMENT
Programme Perfomance Report(non-financials) for Fourth Quarter of FY 2025/26 (as at 30th June 2026)
Programme 1: Housing Development and Human Settlement
Outcome: Increased access to affordable and decent housing as well as enhanced estates management services.
Programme | Sub-Programme | Delivery Unit | Key Outputs | Key Performance Indicators | Annual Targets | Actual | Variance | Remarks
Housing Development and Human Settlement | Delivery of Affordable and social housing units | Housing Department | Affordable Housing | % completion works of 217,654 affordable housing units | 52 | 20 | -32 | •540 units which comprise 220 units in Milimani(lurambi) ,220 units in Emgwen and 100 units in Gichugu completed and handed over, while 1,380 units in following sites;60 units in Mabera, 220 units in each of the sites in Elburgon, Bahati, Nanyuki, Milimani (Vihiga), Chepalungu and Kidiwa phase I are substantially complete awaiting handover. •97,065 units ongoing at average of 54% completion level. •52,054 units are currently in various stages of progress, ranging from the Notification of Intention to Award and Contract Signing to Site Handover and Preliminary Works.
|  | Institutional Housing Department | Institutional housing | % completion works of 23,672 police housing units | 20 | 4 | -16 | Projects ongoing at average 4% completion level
|  |  |  | % completion of works on 10,033 kenya defence forces (KDF) housing units | 15 | 10 | -5 | 10,105 units ongoing as follows; 4,736 at Embakasi Garison-16.16%,1,458 at Lang’ata Barack-7.23% and 3,839 at Kahawa Baracks-19.77%
|  |  |  | % completion works of 31,592 student hostel units | 15 | 10 | -5 | 45,068 student hostel units(180,273 bed capacity) are ongoing at an average of 9% completion level
|  | Slum Upgrading department | Social housing | % completion of 80,909 social housing units | 35 | 27 | -8 | •4,536 bedsitter units Comprising 3,240 lot 1 Call of No. 3 and 1,296 lot 1 Call of 2 in Mukuru Meteological site completed and handed over - 100% . Average 17% for ongoing 54,547 social Housing Units projects •4,054 housing units at Kibera Soweto East Zone ‘B - 84% •3,024 No. one-bedroom units at Mukuru Meteorological site - 62% •1,536 No. Two Bedrooms housing units at Mukuru Meteorological site Lot 3 (Call off No. 1) - 64% •1,536 No. two (2) bedroom housing units at Mukuru Meteorological site Lot 3 (Call off No. 2) - 57% •1,536 No. two (2) bedroom housing units at Mukuru Meteorological site Lot 3 (Call off No. 3) - 18% •Michida Boys Primary sch - 10% Social Housing •Kibra Lot 1-5 - average of 3.8% •Kasarani lot 1-4 - Average of 9.25% •Mathare Lot 1 - 6% Mathare Lot 2-7% •Kamiti Lot 1 - 5% •Kamiti Lot 2 - 38%
|  |  | Physical and social associated infrastructure | No of floodlights installed | 50 | 39 | -11 | 101 No. Floodlights ongoing in various sites while 39No. are installed to completion in various sites
|  |  |  | No of markets constructed | 185 | 8 | -177 | •27 ESP markets ongoing at averege of 50% completion level. 8 No. completed projects Kahawa, Mogotio, Nakuru Multipurpose, Iten, Matharu, Kobodo, Kijebi and Mirangine.
|  |  |  | No. of classrooms constructed | 35 | 0 | -35 | 20 classrooms under construction, the rest under procurement
|  |  |  | No. of multipurpose halls constructed in schools | 1 | 2 | 1 | 2no. Changamwe Youth Centre 100% complete.
|  |  |  | No. of domitories constructed | 3 | 3 | 0 | 3 No. dormitory blocks completed in mlimani primary, Nakuru County
|  |  |  | kms of access roads constructed | 15 | 0.58 | -14.42 | Access road to Ndenderu Market 100% complete. Total 6.65km Road Ongoing. 1. Njathani-Bustani : 0% 2. Gakurwe Market : 6% 3. Karuri Mkt & Kihara Modern Mkt : 20% 4. Mukuyu Soko ya Mbuzi : 1.5% 5. Mukuyu Mkt : 20%
|  |  |  | No. of social halls constructed | 2 | 0 | -2 | Oyugis, Thalatha Rocky playground,and Utawala social halls at Procurement stage
|  |  |  | No. of health centres constructed | 1 | 1 | 0 | Construction at 100% in Unjiru health center, Nyeri County
|  |  |  | No. of footbridges constructed | 2 | 2 | 0 | 2 No. Kuresoi North 100% Completed. 2. No. Under procurement
|  | Housing Department | Compliance with treaties and conventions on human settlement | No. of fora reports prepared | 3 | 1 | -2 | New Urban Agenda forum report prepared
|  | Civil Servants Housing Scheme | Mortgage Disbursed to Civil Servants | No. Civil servants mortgage beneficiaries | 200 | 93 | -107 | Ksh 593,960,722.58 worthy of mortgage disbursed.
|  | Rural Housing Department | Low-cost housing development skills | No. of Constituency ABMT centers. | 11 | 0 | -11 | No Centres constructed during the quarter
|  |  |  | No. of new trainees on ABMT | 2800 | 0 | -2800 | No new trainees during the quarter
| Kenya Informal settekement Improvement project | KISIP | Secured of land tenure in selected informal settlements | No. of Local Physical Development and Land Use Plans (LPDP) | 20 | 25 | 5 | • Approved plans are for Tana River County (2); Kwale County (3); Nandi (6) Taita Taveta (4), Embu (3); Kisii (3) and Machakos (4).
|  |  |  | Kms of access road constructed | 30 | 33.648 | 3.648 | • Roads improved in Uasin Gishu-3.88km; Trans Nzoia- 4.04km; Elgeyo Marakwet-2.08km; Tharaka Nithi-0.97km; Kakamega -0.78km; Kisumu – 0.68km; Nyamira -1.52km; Kiambu - 0.65km; Nandi – 2.4 km; Nyeri (2.345 km); Taita Taveta (1.29 kms); Kajiado (2.22 kms); Mombasa (6.1 kms); Homa Bay (7.402km); and Meru (1.171km) • There is under performance caused by delays in approval of County Government Additional Allocation (CGAA) Act limiting disbursable amounts to counties posing cash flow challenges for the works contract
|  |  |  | No. of youth engaged in Labour Intensive Community Works | 4000 | 4200 | 200 | The labour numbers are recorded from all KISIP2 interventions that include: Digital Public Works; Social Emotional Skills Training; Infrastructure works; Community Development Plans preparation and implementation; Surveying & Planning works; and Preparation of County specific strategy development and mapping of slums
| Estates Management | Estates Department | Government houses refurbished | No. of units refurbished | 500 | 220 | -280 | Units refurbished across the country.During fourth quarter ongoing refurshiment include ; proposed repairs and decorations to directorate of criminal investigations training school housing units(275 units) and proposed repairs to 372 units at Ruiru presidential escort camp
Programme 2: urban and metropolitan development
Outcome: Sustainable urban planning, development and management
Programme | Sub-Programme | Delivery Unit | Key Outputs | Key Performance Indicators | Target 2025/2026 | Actual | variance | Remarks
Urban and metropolitan development | Urban development and planning services | Urban Development Department | second kenya urban support programme (KUSPII) | National Urban Development Policy Reviewed | 1 | 0 | -1 | Its under review, taskforce in place, currently working on metropolitan area frameworks to Policy; procurement of a consultant to support process at EOI shortlist.
|  |  |  | No. of Counties receiving UIG | 45 | 45 | 0 | A total of Kshs 1.17 billion Urban Institutional Grant (UIG) was disbursed with each county receiving Kshs 26 million (Gazette Notice No. 9219 of 19th June 2026).
|  |  |  | No. of Municipalities receiving UDG | 43 | 27 | -16 | A total of Kshs 3,592,332,444 Urban Development Grant (UDG) was disbursed to only 27 municipalities due to limited budget (Gazette Notice No. 9827 of 30th June 2026). Disbursement to the remaining eligible municipalities to be effected in FY 2026/27.
|  | KISRP | Implementation of Kenya informal settlement redevelopment programme( KISRP) in Siaya, Kilifi and Kajiado | No. of Settlements surveyed/Resurveyed | 3 | 0 | -3 | TORs preparred, 3 Draft Layout Plans prepared in house
|  |  |  | Kms of access roads upgraded to Bitumen standards | 2 | 0 | -2 | 1. Needs analysis completed, designs done, and tender documents prepared. 2. Procurement awaits approval from the development partner, AICS. First stage of approval was NPCT which was obtained and now awaits the second stage from AICS headquarters in Rome.
|  |  |  | No. of dispensaries constructed | 3 | 0 | -3 | Priorities for the target settlement changed. 1. In Prison-Kiwandani, the residents obtained alternative funding for dispensary, and therefore, identified Junior Secondary School as a replacement. The project awaits approval of AICS headquarters in Rome. 2. In Awelo, the County Government of Siaya has plans to develop a better facility. Therefore, they suggested the expansion of the scope for the road, fro,m 1,3km to 1,9km. The project awaits approval of AICS headquarters in Rome. 3. In Kajiado, planning of the settlement which was a precursor for the dispensary construction experienced unforeseen challenges, therefore, making implementation impossible within the reporting period.
Prepared by: |  | Signed:
Approved by: |  | Signed:
Date: