## SUMMARY
S/No. | Region | No. of Projects | No. of Social Housing Units | No. of Markets | No. of Social Infrastucture | No of Social Projects | Total Contract Sum | No. of Counties | AVERAGE PROGRESS%
1 | Central | 11 | 0 | 3 | 16 | 0 | 538058101.2 | 4 | 45.96%
2 | Coast & North Eastern | 8 | 0 | 2 | 12 | 0 | 377233662.9 | 7 | 78.75%
3 | Eastern | 9 | 0 | 1 | 8 | 0 | 196401674 | 4 | 46.25%
4 | Metropolitan | 16 | #REF! | 3 | 21 | 0 | #REF! | 3 | 63.06%
5 | Nairobi | 42 | 50672 | 0 | 9 | 4 | 146809027840 | 1 | 44.38%
6 | Nyanza | 18 | 0 | 8 | 23 | 0 | 392331410 | 3 | 84.94%
7 | Rift Valley - North | 9 | 0 | 2 | 13 | 0 | 196398573 | 4 | 58.67%
8 | Rift Valley - South | 30 | 2480 | 13 | 31 | 0 | 6108037111 | 5 | 56.17%
9 | West Rift Valley | 6 | 0 | 3 | 8 | 0 | 180861679 | 2 | 85.5%
10 | Western | 8 | 0 | 4 | 7 | 0 | 222890143 | 3 | 72.6%
| Grand Total | 157 | #REF! | 39 | 148 | 4 | #REF! | 36

## UNDER PROCUREMENT
S/No. | Project Name | County | Constituency | Project Type | Contractor | Consultant | No. of Units | Start Date | End Date | Project Estimated Cost (KES) | Completion Status (%) | Remarks
2 | Installation of 2No. solar powered floodlight in Toroton Centre and Kacheliba Centre in Kipkelion West constituency,Kericho County | Kericho | Kipkelion West | Highmast |  |  | 2 | TBD | TBD | 16000000 | 0% | Evaluation
3 | Installation of 240No. solar street lights along Mutarakwa- Thogoto road in Ndeiya Constituency | Kiambu | Ndeiya | highmast |  |  | 1 | TBD | TBD | 29543204 | 0% | Awarded
4 | Installation of 4No. solar powered floodlight in Rafiki shopping centre (1No.), Kapnyangale centre(1No.), and East Gate (2No.) in Nakuru County | Nakuru | Various | Highmast |  |  | 4 | TBD | TBD | 32000000 | 0% | Evaluation
5 | Installation of 3No. solar powered floodlight in Sirisia Market, Butonge market and Malakisi Market, Sirisia Constituency in Bungoma County | Bungoma | Sirisia | Highmast |  |  | 3 | TBD | TBD | 24868287 | 0% | Contracted | 211
6 | Installation of 1No. solar powered floodlight in Kariobangi , Mwatate Constituency in Taita Taveta County | Taita Taveta | Mwatate | Highmast |  |  | 1 | TBD | TBD | 8000000 | 0% | Evaluation
7 | Installation of 1No. solar powered floodlight in Bura Market , Mwatate Constituency in Taita Taveta County | Taita Taveta | Mwatate | Highmast |  |  | 1 | TBD | TBD | 8000000 | 0% | Evaluation
8 | Installation of 1No. solar powered floodlight in Kamtonga Trading centre , Mwatate Constituency in Taita Taveta County | Taita Taveta | Mwatate | Highmast |  |  | 1 | TBD | TBD | 8000000 | 0% | Evaluation
9 | Installation of 4No. solar powered floodlight in Kariakoo Central village, Ikanga shopping centre, Maweni Village and Mwalangi shopping centre, Voi Constituency in Taita Taveta County | Taita Taveta | Mwatate | Highmast |  |  | 4 | TBD | TBD | 32000000 | 0% | Evaluation
11 | Proposed construction of 1No. Modern market at Hagdera in Fafi Constituency in Garissa County | Garissa | Fafi | Market |  |  | 1 | TBD | TBD | 150000000 | 0% | Evaluation
12 | Construction 1No. Market and supporting facilities at Abuor (Kolenya) | Migori | Rongo | Market |  |  | 1 | TBD | TBD | 30000000 | 0% | Evaluation
13 | Construction of 1No. market, offices, ablution block and external works in Kasarani Contituency | Nairobi | Kasarani | Market |  |  | 1 | TBD | TBD | 30000000 | 0% | Evaluation
14 | Market and Associated infrastructure in Transmara East Njipishi in Narok County | Narok | Transmara East Njipishi | Market |  |  | 1 | TBD | TBD | 30000000 | 0% | Evaluation
15 | Market and Associated infrastructure in Transmara West at Angata Bariko in Narok County | Narok | Angata Bariko | Market |  |  | 1 | TBD | TBD | 30000000 | 0% | Evaluation
16 | Construction of 1No. market shed, offices, ablution block and external works at Nyagondo in Gem Constituency | Siaya | Gem | Market |  |  | 1 | TBD | TBD | 30000000 | 0% | Evaluation
17 | Construction of 1No. market and supporting facilities at Obambo, in Alego Usonga, Siaya County - To be moved to Ting Wangi | Siaya | Alego Usonga | Market |  |  | 1 | TBD | TBD | 30000000 | 0% | Evaluation
18 | Proposed construction of market shed and supporting facilities at Njukini, Taita Taveta County | Taita Taveta | Taveta | Market |  |  | 1 | TBD | TBD | 30000000 | 0% | Evaluation
19 | Proposed upgrading to cabro standards of access roads - Karuri market access roads - Karuri market access road and Kihara modern market access road in Kiambaa Constituency, Kiambu County | Kiambu | Kiambaa | Social and Physical Infrastructure |  |  | 1 | TBD | TBD | 61795839 | 0% | Contracted
20 | Construction of Mumbuni Health Centre in Mwala Constituency, Machakos County | Machakos | Mwala | Social and Physical Infrastructure |  |  | 1 | TBD | TBD | 82036337.67 | 0% | Awarded
21 | Construction of 1No. Market and supporting facilities at Kajuki in Chuka Igamba Ngombe Constituency. | Tharaka Nithi | Chuka Igamba Ngombe | Market |  |  | 1 | TBD | TBD | 25432490 | 0% | Awarded
22 | Installation of 2No. 20m high Solar powered floodlight at Kapsokwony Town in Mt. Elgon Constituency, Bungoma County | Bungoma | Mt. Elgon | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
23 | Installation of 2No. 20m high Solar powered floodlight at Kanduyi Town in Kanduyi Constituency, Bungoma County | Bungoma | Kanduyi | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
24 | Installation of 1No. 20m high solar powered floodlights in Kolol market in Keiyo South constituency, Elgeyo Marakwet County | Elgeyo Marakwet | Keiyo South | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
25 | Installation of 2No. 20m high solar powered floodlights in Kocholwo market in Keiyo South constituency, Elgeyo Marakwet County | Elgeyo Marakwet | Keiyo South | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
26 | Installation of 1No. 20m high solar powered flood lights at Lilies- Iten in Keiyo North Constituency, Elgeyo Marakwet County | Elgeyo Marakwet | Keiyo North | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
27 | Installation of 2No. 20m high Solar powered floodlight at Kitengela Town in Kajiado East Constituency, Kajiado County | Kajiado | Kajiado East | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
28 | Installation of 1No. 20m high Solar Powered High Mast Floodlight at Kipchimchim market in Ainamoi Contituency, Kericho County | Kericho | Ainamoi | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
29 | Installation of 2No. 20m high Solar powered floodlight at Brooke Town in Ainamoi Constituency, Kericho County | Kericho | Ainamoi | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
30 | Installation of 2No. 20m high Solar powered floodlight at Litein Town in Bureti Constituency, Kericho County | Kericho | Bureti | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
31 | Installation of 2No. 20m high Solar powered floodlight at Chepseon Town in Kipkelion East Constituency, Kericho County | Kericho | Kipkelion East | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
32 | Installation of 2No. 20m high Solar powered floodlight at Sondu Town in Soin Sigowet Constituency, Kericho County | Kericho | Soin Sigowet | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
33 | Installation of 2No. 20m high Solar powered floodlight at Chepnyogaa Centre in Belgut Constituency,Kericho County | Kericho | Belgut | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
34 | Installation 1No. 20m high Solar powered Highmast floodlight at Pesi in Laikipia West Constituency | Laikipia | Laikipia West | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
35 | Installation of 2No. 20m high Solar powered floodlight at Lounyek Town in Laikipia North Constituency, Laikipia County | Laikipia | Laikipia North | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
36 | Installation of 2No. 20m high Solar powered floodlight at Kwa Mwaura in Laikipia East Constituency, Laikipia County | Laikipia | Laikipia East | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
37 | Installation of 2No. 20m high Solar powered floodlight at Male Centre- Tigithi in Laikipia East Constituency, Laikipia County | Laikipia | Laikipia East | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
38 | Installation of 2No. 20m high Solar powered floodlight at African Location in Laikipia West Constituency, Laikipia County | Laikipia | Laikipia West | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
39 | Installation of 1No. 20m high Solar powered floodlights in Laisamis Constituency, Marsabit County | Marsabit | Laisamis | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
40 | Installation of 1No. High mast Floodlights in Moyale, Marsabit County | Marsabit | Moyale | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
41 | Installation of 1No. 20m high solar powered floodlights in Mwichiune market, South Imenti constituency, Meru County | Meru | South Imenti | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
42 | Installation of 1No. 20m high solar powered floodlight in Shauri Yako Informal Settlement, Meru County | Meru | Imenti North | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
43 | Installation of 1No. 20m high solar powered floodlight in Abuor (Kolenya) market,Rongo constituency,Migori County | Migori | Rongo | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
44 | Installation of 2No. 20m high Solar powered floodlight at Rongo University in Rongo Constituency, Migori County | Migori | Rongo | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
45 | Installation of 2No. High mast Floodlights in Changamwe Youth Centre (1No. 30m high), Mombasa County | Mombasa | Changamwe | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
46 | Installation of 1No. High mast Floodlights in Bombolulu, Mombasa County | Mombasa | Mvita | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
47 | Installation of 1No. High mast Floodlights in Swaleh Khalid, Mombasa County | Mombasa | Jomvu | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
48 | Installation of 2No. 20m high Solar powered floodlight at Mirindiki Town in Nyali Constituency, Mombasa County | Mombasa | Nyali | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
49 | Installation of 1No. 20m high solar powered flood lights at Maraba Market in Tinderet Constituency, Nandi County | Nandi | Tinderet | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
50 | Installation of 2No. 20m high Solar powered floodlight at Nandi Hills Town in Nandi Hills Constituency, Nandi County | Nandi | Nandi Hills | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
51 | Installation of 2No. 20m high Solar powered floodlight at Mosoriot Town in Chesumei Constituency, Nandi County | Nandi | Chesumei | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
52 | Proposed Construction of Kapsabet Bus Park, Nandi county | Nandi | Emgwen | Social and Physical Infrastructure |  |  | 1 | TBD | TBD | 120000000 | 0% | Advertised
53 | Installation of 1No. 20m high solar powered floodlight in Transmara West Angata Bariko market, Angata Bariko constituency,Narok County | Narok | Angata Bariko | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
54 | Installation of 1No. 20m high Solar powered floodlight at Esoit Town in Kilgoris Constituency, Narok County | Narok | Kilgoris | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
55 | Installation of 2No. 20m high Solar powered floodlight at Ntulele Town in Narok East Constituency,Narok County | Narok | Narok East | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
56 | Installation of 2No. 20m high Solar powered floodlight at Narok Town in Narok North Constituency,Narok County | Narok | Narok North | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
57 | Installation of 1No. 20m high Solar powered floodlight at Murkan Junction in Kilgoris Constituency, Narok County | Narok | Kilgoris | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
58 | Installation of 2No. 20m high Solar powered floodlight at Enosaen Centre in Kilgoris Constituency,Narok County | Narok | Kilgoris | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
59 | Installation of 2No. 20m high Solar powered floodlight at Lolgorioan Town in Kilgoris Constituency,Narok County | Narok | Kilgoris | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | Advertised
60 | Proposed Construction of Kilgoris Bus Park- Narok county | Narok | Kilgoris | Social and Physical Infrastructure |  |  | 1 | TBD | TBD | 120000000 | 0% | Advertised
61 | Installation of 1No. 20m high Solar powered floodlight at Takitech center in Emurua Dikirr Constituency, Narok County | Narok | Emurua Dikirr | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
62 | Intstallation of 1No. 20m high solar powered flood lights at West Mugirango Constituency, Nyamira | Nyamira | West Mugirango | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
63 | Intstallation of 1No. 20m high solar powered flood lights at Esise Market in Ekebuse sub-location, Nyamira | Nyamira | Borabu | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
64 | instalation of 1No. 20m high Solar powered Highmast floodlights at Nyarugumu shopping centre in Nyeri Town Constituency. | Nyeri | Nyeri Town | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
65 | Installation of 1No. 20m high solar powered floodlight in Kairuthi Shopping Centre (Iriaini ward) in Othaya Constituency, Nyeri County | Nyeri | Othaya | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
66 | Installation of 1No. 20m high solar powered flood lights in Mukurweini Constituency, Nyeri County | Nyeri | Mukurweini | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
67 | Installation of 1No. 20m high solar powered flood lights in Githura center, Kieni Constituency, Nyeri County | Nyeri | Kieni | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
68 | Installation of 1No. 20m high solar powered floodlights in Madogo in Tana River County | Tana River | Bura | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
69 | Installation of 1No. 20m high solar powered floodlights in Garsen Mala Koteni in Tana River County | Tana River | Garsen | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
70 | Installation of 1No. 20m high solar powered floodlights in Makaburini, Tana River County | Tana River | Galole | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
71 | Installation of 1No. 20m high solar powered floodlight in Kasoiyo center in Baringo Central Constituency, Baringo County | Baringo | Baringo Central | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
72 | Installation of 2No. 20m high Solar powered floodlight in Baringo North Constituency, Baringo County | Baringo | Baringo North | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
73 | Installation of 2No. 20m high Solar powered floodlight in Kabarnet Constituency, Baringo County | Baringo | Kabarnet | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
74 | Installation of 1No. 20m high solar powered floodlight in Mogotio ESP in Mogotio Constituency, Baringo County | Baringo | Mogotio | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
75 | Installation of 1No. 20m high Solar powered floodlights in Silibwet, Bomet Central Constituency, Bomet County | Bomet | Bomet Central | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
76 | Installation of 2No. 20m high Solar powered floodlight at Silibwet Town in Bomet Central Constituency, Bomet County | Bomet | Bomet Central | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
77 | Installation of 1No. 20m high Solar powered high mast flood lights at Kolongei in Konoin Constituency, Bomet County | Bomet | Konoin | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
78 | Installation of 2No. 20m high Solar powered floodlight at Kurkuton market in Konoin Constituency, Bomet County | Bomet | Konoin | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
79 | Installation of 1No. 20m high Solar powered floodlight at Mogogosiek Township in Konoin Constituency, Bomet County | Bomet | Konoin | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
80 | Installation of 1No. 20m high Solar powered floodlights in Sotik Constituency, Bomet County | Bomet | Sotik | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
81 | Installation of 2No. 20m high Solar powered floodlight at Sotik Town in Sotik Constituency, Bomet County | Bomet | Sotik | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
82 | Installation of 2No. 20m high Solar powered floodlight at Chebole in Sotik Constituency, Bomet County | Bomet | Sotik | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
83 | Installation of 1No. 20m high Solar powered floodlights in Budalangi, Busia County | Busia | Budalangi | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
84 | Installation of 1No. 20m high Solar powered floodlights in Malaba, Busia County | Busia | Teso North | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
85 | Installation of 2No. 20m high Solar powered floodlight at Kocholwo in Keiyo South Constituency, Elgeyo Marakwet County | Elgeyo Marakwet | Keiyo South | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
86 | Installation of 2No. 20m high Solar powered floodlight at Labot Kamoi in Marakwet East Constituency, Elgeyo Marakwet County | Elgeyo Marakwet | Marakwet East | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
87 | Installation of 1No. 20m high solar powered floodlights in Njukiri, Manyatta constituency, Embu County | Embu | Manyatta | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
88 | Installation of 1No. 20m high solar powered floodlight in Hagdera modern market, Fafi constituency,Garissa County | Garissa | Fafi | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
89 | Installation of 1No. 20m high Solar powered floodlights in Ziwani in Garissa County | Garissa | Garissa Township | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
90 | Installation of 1No. 20m high solar powered floodlight in Kapita, Homabay Town constituency,Homabay County | Homabay | Homabay Town | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
91 | Installation of 1No. 20m high solar powered floodlight in Karachuonyo constituency,Homabay County | Homabay | Karachuonyo | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
92 | Installation of 1No. 20m high solar powered floodlight in Isiolo North Constituency, Isiolo County | Isiolo | Isiolo North | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
93 | Installation of 1No. 20m high solar powered floodlight in Isiolo South Constituency, Isiolo County | Isiolo | Isiolo South | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
94 | Installation of 1No. 20m high solar powered floodlight in Matete market, Lugari constituency,Kakamega County | Kakamega | Lugari | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
95 | Installation of 1No. 20m high solar powered floodlight in Malava Town, Malava constituency,Kakamega County | Kakamega | Malava | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
96 | Installation of 1No. 20m high solar powered flood lights in Kipkelion East Constituency, Kericho County | Kericho | Kipkelion East | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
97 | Installation of 1No. 20m high solar powered floodlight in St. Francis Mukinyai Centre in Gatundu North Constituency, Kiambu County | Kiambu | Gatundu North | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
98 | Access and Upgrading to cabro of banana backstreet in Kiambaa in Kiambu County | Kiambu | Kiambaa | Social and Physical Infrastructure |  |  | 1 | TBD | TBD | 40552553 | 0% | In EGP awaiting requisition
99 | Installation of 1No. 20m high solar powered flood lights in Kiambu town ,Kiambu Town Constituency, Kiambu County | Kiambu | Kiambu Town | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
100 | Installation of 2No. 20m high Solar powered floodlight at Ruiru Town in Ruiru Constituency,Kiambu County | Kiambu | Ruiru | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
101 | Installation of 3No. 20m high Solar powered floodlight at Kamiti corner in Ruiru Town in Thika Constituency,Kiambu County | Kiambu | Ruiru | Highmast |  |  | 3 | TBD | TBD | 15000000 | 0% | In EGP awaiting requisition
102 | Installation of 2No. 20m high Solar powered floodlight at Stepping Stone road in Thika Constituency, Kiambu County | Kiambu | Thika | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
103 | Access and Upgrading to cabro of Ngoingwa Market in Thika Town in Kiambu County | Kiambu | Thika Town | Social and Physical Infrastructure |  |  | 1 | TBD | TBD | 15728302 | 0% | In EGP awaiting requisition
104 | Installation of 1No. 20m high solar powered floodlight at Makaburini in Malindi Constituency, Kilifi County | Kilifi | Malindi | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
105 | Installation of 1No 20m high solar powered flood lighting at Mwea Constituency, Kirinyaga County | Kirinyaga | Mwea | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
106 | Installation of 2No. 20m high Solar powered floodlight at Igare Market in Bobasi Constituency, Kisii County | Kisii | Bobasi | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
107 | Installation of 1NO. 20m high solar powered highmast floodlights at Nyamasege Market in Bomachoge Chache Constituency, Kisii County | Kisii | Bomachoge Chache | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
108 | Installation of 1No. 20m high solar powered floodlight in Muhoroni Constituency, Kisumu County | Kisumu | Muhoroni | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
109 | installation of 1No. 20m high solar powered flood lights at Kyatune market in Kitui South Constituency. | Kitui | Kitui South | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
110 | Installation of 1No. 20m high solar powered flood lights at Mitinyani Market in Kitui West Constituency, Kitui County | Kitui | Kitui West | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
111 | Installation of 1No 20m high solar powered highmast flood lighting structures in Mwingi Town | Kitui | Mwingi North | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
112 | Installation of 1No. 20m high solar powered flood lights at Migwani Market in Mwingi West Constituency, Kitui County | Kitui | Mwingi West | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
113 | Installation of 1No. 20m high Solar powered floodlight in Shimoni, Kinango Constituency, Kwale County | Kwale | Kinango | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
114 | Installation of 1No. 20m high Solar powered floodlight in Lunga Lunga, Lunga Lunga Constituency, Kwale County | Kwale | Lunga Lunga | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
115 | Installation of 1No. 20m high Solar powered floodlight in Shimba Hills, Matuga Constituency, Kwale County | Kwale | Matuga | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
116 | Installation of 1No. 20m high Solar powered floodlight in Ngombato, Msambweni Constituency, Kwale County | Kwale | Msambweni | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
117 | Installation of 1No. 20m high Solar powered highmast flood lights at Mtagawanda Village in Lamu East constituency. | Lamu | Lamu East | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
118 | Installation of 1No. 20m high Solar powered floodlight in Hindi, Mpeketoni in Lamu County | Lamu | Lamu West | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
119 | Installation of 2No. 20m high Solar powered floodlight at Katoloni in Machakos Constituency, Machakos County | Machakos | Machakos | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
120 | Installation of 1No. 20m high solar powered floodlight in Muumandu in Machakos Town Constituency, Machakos County | Machakos | Machakos Town | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
121 | Installation of 2No. 20m high Solar powered floodlight at Muumandu in Machakos Town Constituency, Machakos County | Machakos | Machakos Town | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
122 | Installation of 2No. 20m high Solar powered floodlight at Katheka in Machakos Town Constituency, Machakos County | Machakos | Machakos Town | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
123 | Provision of water and sanitation infrastructure connection from Mombasa expressway line to Mavoko SNP & AHP in Mavoko SNP, Machakos County | Machakos | Mavoko | Social and Physical Infrastructure |  |  | 1 | TBD | TBD | 100000000 | 0% | In EGP awaiting requisition
124 | Installation of 1No. 20m high Solar powered floodlight in Joska Shopping Centre, Mavoko Constituency, Machakos County | Machakos | Mavoko | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
125 | Installation of 1No. 20m high solar powered floodlight in Mwala market in Mwala Constituency, Machakos County | Machakos | Mwala | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
126 | Installation of 1No. 20m high solar powered floodlight in Itithini and Kamale market sheds in Yatta Constituency,Machakos County | Machakos | Yatta | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
127 | Installation of 1No. 20m high solar powered floodlight in Musalala market in Kaiti Constituency,Makueni County | Makueni | Kaiti | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
128 | Installation of 1No. 20m high solar powered floodlight in Ulilinzi shopping centres in Kibwezi East Constituency,Makueni County | Makueni | Kibwezi East | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
129 | Installation of 1No. 20m high solar powered floodlight in Kikumini in Kibwezi West Constituency,Makueni County | Makueni | Kibwezi West | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
130 | Installation of 1No. 20m high solar powered floodlight in Nzeveni in Kilome Constituency,Makueni County | Makueni | Kilome | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
131 | Installation of 1No. 20m high solar powered floodlight in Kwa Mutula in Makueni Constituency,Makueni County | Makueni | Makueni | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
132 | Installation of 1No. 20m high solar powered floodlight in Watuka market in Mbooni Constituency,Makueni County | Makueni | Mbooni | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
133 | Installation of 1No. 20m high Solar powered floodlights in Banissa Constituency, Mandera County | Mandera | Banissa | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
134 | Installation of 1No. 20m high solar powered floodlight in Alungu Town in Lafey Constituency, Mandera County | Mandera | Lafey | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
135 | Installation of 1No. 20m high solar powered floodlights in Libehiya wards in Mandera East Constituency, Mandera County | Mandera | Mandera East | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
136 | Installation of 1No. 20m high solar powered flood lights at Garsey Market in Mandera North Constituency, Mandera County | Mandera | Mandera North | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
137 | Installation of 1No. 20m high solar powered High mast floodlights at wargadud hospital in Mandera South Constituency | Mandera | Mandera South | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
138 | Installation of 1No 20m high solar powered highmast flood lighting in Takaba Town in Mandera West Constituency | Mandera | Mandera West | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
139 | Installation of 1No. 20m high Solar powered floodlight at Tabaka Town in Mandera West Constituency, Mandera County | Mandera | Mandera West | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
140 | Installation of 2No. 20m high Solar powered floodlight at Gither Town in Mandera West Constituency,Mandera County | Mandera | Mandera West | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
141 | Installation of 1No. 20m high solar powered flood lights at Kabati Town in Kandara Constituency, Muranga County | Muranga | Kandara | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
142 | Installation of 1NO. 20m high solar powered highmast floodlights at Karurumo Centre in Kagema Constituency ,Murang'a County | Muranga | Kangema | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
143 | Installation of 1No. 20m high flood light Kora in Mathioya Constituency | Muranga | Mathioya | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
144 | Installation of 1No. 20m high flood light Mjini informal settlement in Maragua Constituency | Muranga | Maragua | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
145 | Installation of 1No. 20m high flood light at Ngonda Kigumo in Mathioya Constituency | Muranga | Ngonda Kigumo | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
146 | Proposed construction of Kitchen, Dining hall, Administation block and Associated works at Waitua Secondary School Kandara Constituency | Murang'a | Kandara | Social and Physical Infrastructure |  |  | 1 | TBD | TBD | 60000000 | 0% | In EGP awaiting requisition
147 | Completion of dormitory at Mukerenju Special School in Kabati Town, Kandara Constituency, Muranga County | Murang'a | Kandara | Social and Physical Infrastructure |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
149 | Proposed EPC + F Social Housing Units and associated civil works at along the Nairobi Railway Line In Nairobi County | Nairobi | Langata | Social Housing |  |  | 5655 | TBD | TBD | 9000000000 | 0% | In EGP awaiting requisition
150 | Installation of 1No. 20m high solar powered floodlight in Kayole Centre in Embakasi Central Constituency, Nairobi County | Nairobi | Embakasi Central | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
151 | Installation of 1No. 20m high Solar powered floodlight at Embakasi Central in Embakasi Central Constituency, Nairobi County | Nairobi | Embakasi Central | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
152 | Installation of 1No. 20m high solar powered flood lights at Kwa Maji Estate in Embakasi West | Nairobi | Embakasi West | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
153 | Installation of 1No. 20m high solar powered flood lights at Utawala - Githunguri in Embakasi East | Nairobi | Embakasi East | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
154 | Construction of Social Hall in Utawala, Nairobi County | Nairobi | Embakasi East | Social and Physical Infrastructure |  |  | 1 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
155 | Installation of 1No. 20m high Solar powered floodlights in Kahawa Soweto in Nairobi County | Nairobi | Roysambu | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
156 | Installation of 1No. 20m high Solar powered floodlight at Westlands in Westlands Constituency, Nairobi County | Nairobi | Westlands | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
158 | Installation of 1No. 20m high Solar powered highmast flood lighting in Kuresoi North Constituency | Nakuru | Kuresoi North | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
159 | Installation of 1No. 20m high solar powered floodlight in Elburgon Salama Market in Molo Constituency, Nakuru County | Nakuru | Molo | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
160 | Proposed Bondeni Maternity Hospital in Nakuru County | Nakuru | Nakuru Town East | Social and Physical Infrastructure |  |  | 1 | TBD | TBD | 60000000 | 0% | In EGP awaiting requisition
161 | Installation of 1No 20m high solar powered flood lighting at Mzee Wanyama in Nakuru Town East Constituency | Nakuru | Nakuru Town East | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
162 | Installation of 2No. 20m high Solar powered floodlight at Roda Estate in Nakuru East Constituency, Nakuru County | Nakuru | Nakuru Town East | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
163 | Installation of 2No. 20m high Solar powered floodlight in Rongai Constituency, Nakuru County | Nakuru | Rongai | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
164 | Installation of 1No. 20m high Solar powered Highmast floodlights at Tumaini town in Olkalou Constituency, Nyandarua County | Nyandarua | Ol Kalau | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
165 | Installation of 1No. 20m high Solar powered Highmast floodlights at Kiamaina centre in Nyandarua Central Constituency, Nyandarua County | Nyandarua | Nyandarua Central | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
166 | Installation of 1No. 20m high solar powered floodlight in Ting Wangi market,Alego Usonga constituency,Siaya County | Siaya | Alego Usonga | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
167 | Installation of 1No. 20m high solar powered floodlight in Nyagondo market,Gem constituency,Siaya County | Siaya | Gem | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
168 | Installation of 1No. 20m high Solar powered floodlight at Ugenya Diploma Teacher's College in Ugenya Constituency, Siaya County | Siaya | Ugenya | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
169 | Installation of 1No. 20m high solar powered floodlight in Njukini market, Taveta constituency,Taita Taveta County | Taita Taveta | Taveta | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
170 | Installation of 1No. 20m high solar powered flood lights at Wundanyi market, in Wundanyi Constituency, Taita Taveta County | Taita Taveta | Wundanyi | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
171 | Installation of 1No. 20m high solar powered floodlight in Kajuki market, Chuka Igamba Ngombe constituency,Tharaka Nithi County | Tharaka Nithi | Chuka Igamba Ngombe | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
173 | Installation of 2No. 20m high Solar powered floodlight at Chilanga Town in Cherangany Constituency,Trans Nzoia County | Trans Nzoia | Cherangany | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
174 | Installation of 2No. 20m high Solar powered floodlight at Cheptantany Centre in Endebess Constituency,Trans Nzoia County | Trans Nzoia | Endebess | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
175 | Installation of 2No. 20m high Solar powered floodlight at Kitale Town in Kitale Constituency,Trans Nzoia County | Trans Nzoia | Kitale | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
176 | Installation of 2No. 20m high Solar powered floodlight at Loima Town in Loima Constituency, Turkana County | Turkana | Loima | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
177 | Installation of 1No. 20m high Solar Powered High Mast Floodlight at Lokichar in Turkana East Contituency, Turkana County | Turkana | Turkana East | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
178 | Installation of 1No. 20m high Solar Powered High Mast Floodlight at Todonyang in Turkana North Contituency, Turkana County | Turkana | Turkana North | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
179 | Installation of 1No. 20m high solar powered floodlight in Ainabkoi ESP Market, Ainabkoi Constituency in Uasin Gishu County | Uasin Gishu | Ainabkoi | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
180 | Installation of 1No. 20m high solar powered floodlight in Lessos Farm trading centre in Kapseret constituency,Uasin Gishu County | Uasin Gishu | Kapseret | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
181 | Installation of 2No. 20m high Solar powered floodlight at Langas Centre in Kapseret Constituency, Uasin Gishu County | Uasin Gishu | Kapseret | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
182 | Installation of 1No. 20m high solar powered floodlight in Cheplaskei in Kesses Constituency ,Uasin Gishu County | Uasin Gishu | Kesses | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
183 | Installation of 2No. 20m high Solar powered floodlight at Kesses Town in Kesses Constituency, Uasin Gishu County | Uasin Gishu | Kesses | Highmast |  |  | 2 | TBD | TBD | 10000000 | 0% | In EGP awaiting requisition
184 | Installation of 1No. 20m high Solar powered floodlight at Cheptiret Market in Kesses Constituency, Uasin Gishu County | Uasin Gishu | Kesses | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
185 | Installation of 1No. 20m high Solar powered floodlight at Moi University Stage Market in Kesses Constituency, Uasin Gishu County | Uasin Gishu | Kesses | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
186 | Installation of 1No. 20m high Solar powered floodlight at Lower Moiben in Moiben Constituency, Uasin Gishu County | Uasin Gishu | Moiben | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
187 | Installation of 1No 20m solar powered high highmast flood lighting at Lower Moiben Market in Soy Constituency | Uasin Gishu | Soy | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
188 | Installation of 1No. 20m high solar powered flood light at Jebrock market(Jepkoyai ward) in Hamisi Constituency, Vihiga County | Vihiga | Hamisi | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
189 | Installation of 1No. 20m high solar powered floodlight in Kotulo in Tarbaj Constituency, Wajir County | Wajir | Tarbaj | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
190 | Installation of 1No 20m high solar powered highmast flood lighting structures in Wagberi and Bulla Alimaow Wajir East | Wajir | Wajir East | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
191 | Installation of 1No. 20m high Solar powered floodlight at Longarkou scheme in Suam ward in Kacheliba Constituency, West Pokot County | West Pokot | Kacheliba | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
192 | Installation of 1No. 20m high Solar powered floodlight in Kapenguria Constituency, West Pokot County | West Pokot | Kapenguria | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
193 | Proposed construction and repair of classroom block and repair of existing classroom at Gitothua primary school in Kiambu County | Kiambu | Ruiru | Social and Physical Infrastructure |  |  | 1 | TBD | TBD | 50000000 | 0% | In EGP awaiting tendering
194 | Proposed construction and repair of existing classrooms at Githurai Kimbo Primary School, Kiambu County | Kiambu | Ruiru | Social and Physical Infrastructure |  |  | 1 | TBD | TBD | 26252253 | 0% | In EGP awaiting tendering
194 |  | Kiambu | Ruiru | Social and Physical Infrastructure |  |  | 1 | TBD | TBD | 26252253 | 0% | In EGP awaiting tendering
196 | Proposed completion of construction of Kiamaina market sheds in Nakuru (Bahati) | Nakuru | Bahati | Markets |  |  | 1 | TBD | TBD | 16786110 | 0% | Under procurement
197 | Proposed completion of construction of multipurpose hall and completion of dormitory at Naivasha boys boarding primary school in Nakuru | Nakuru | Naivasha | Social and Physical Infrastructure |  |  | 1 | TBD | TBD | 15000000 | 0% | Under procurement

## NAIROBI
S/No. | Project Name | County | Constituency | Project Type | Contractor | Consultant | No. of Units | Start Date | End Date | Revised End Date | Project Estimated Cost (KES) | Completion Status (%) | Time Lapsed( %) | Remarks | No. of Workers on Site | Latest Date Updated
SOCIAL HOUSING
1 | Proposed social housing units and associated civil works at Met Site (Lot 1-Bedsitter Units) Nairobi County, (Call off 1-5No. blocks) | Nairobi | Embakasi South | Social Housing | Vaghjiyani Enterprises LTD | Decalogue International LTD | 1080 | 19th August 2021 | 24th January 2025 |  | 1359158644 | 100% | 140% | Complete
2 | Proposed social housing units and associated civil works at Met Site (Lot 1-Bedsitter Units) Nairobi County, 3rd call-off(15 blocks) | Nairobi | Embakasi South | Social Housing | Vaghjiyani Enterprises LTD | Decalogue International LTD | 3240 | 1st September 2023 | 1st September 2025 |  | 4122520143 | 98% | 139% | Ongoing
3 | Proposed Social Housing Units and associated civil works at the MET Site Nairobi under framework agreement (Lot 2 - One Bedroom units) | Nairobi | Embakasi South | Social Housing | Epco Builders Limited | Decalogue International Limited | 3024 | 1st March 2024 | 1st March 2026 |  | 3540673598 | 61% | 115% | Ongoing
4 | Proposed Social Housing Units and associated civil works at the MET Site Nairobi under framework agreement (Lot 3 - Two Bedroom units) - Call-off 1 | Nairobi | Embakasi South | Social Housing | Topchoice Surveillance Limited | Decalogue International Limited | 1536 | 1st March 2024 | 22nd March 2027 |  | 1900536855 | 64% | 75% | Ongoing
5 | Proposed Social Housing Units and associated civil works at the MET Site Nairobi under framework agreement (Lot 3 - Two Bedroom units) - Call-off 2 | Nairobi | Embakasi South | Social Housing | Topchoice Surveillance Limited | Decalogue International Limited | 1536 | 1st March 2024 | 1st March 2026 |  | 1900536855 | 56% | 115% | Ongoing
6 | Proposed Social Housing Units and associated civil works at the MET Site Nairobi under framework agreement (Lot 3 - Two Bedroom units) - Call-off 3 | Nairobi | Embakasi South | Social Housing | Topchoice Surveillance Limited | Decalogue International Limited | 1536 | 15th April 2025 | 15th April 2027 |  | 1900536855 | 18% | 58% | Ongoing
7 | Procurement installation of 54No. lifts at the proposed social housing and associated infrastructure at Mukuru MET site project | Nairobi | Embakasi South | Physical Infrastructure | Topchoice Surveillance Limited |  | 1 | 6th January 2025 | 6th January 2026 |  | 290173213 | 100% | 144% | Complete
8 | Proposed construction of Civil works for roads and other external works in social housing- met site (Lot 1) | Nairobi | Embakasi South | Social and Physical Infrastructure | Pinnie Agency LTD |  | 1 | 25th March 2021 | 8th September 2022 |  | 430970890 | 76% | 359% | Ongoing
9 | Civil & other Associated Works for Social Housing Project at Meteorological Site (Lot 2) | Nairobi | Embakasi South | Social and Physical Infrastructure | Infinity Development Limited |  | 1 | 15th February 2021 | 27th August 2026 |  | 903794568 | 92% | 96% | Ongoing
10 | Proposed construction of outbuilding and associated electromechanical services works for Social Housing Project at Meteorological Site (Lot 3) | Nairobi | Embakasi South | Social and Physical Infrastructure |  |  | 1 | 25th March 2021 | 31st October 2025 |  | 764462962 | 85% | 114% | Ongoing
11 | Completion works in readiness for official handover for Mukuru MET Site Bedsitters Call off 1 | Nairobi | Embakasi South | Social and Physical Infrastructure |  |  | 1 | 2025-04-01 | 2025-05-01 |  | 652443537 | 100% | 1467% | Complete
12 | Completion works in readiness for official handover for Mukuru MET Site Bedsitters Call off 3 | Nairobi | Embakasi South | Social and Physical Infrastructure |  |  | 1 | 2nd March 2026 | 2nd March 2027 |  | 1771638832 | 95% | 29% | Ongoing
13 | Price variation for Mukuru MET One Bedroom Units | Nairobi | Embakasi South | Social and Physical Infrastructure |  |  | 1 | 2025-12-01 | 2026-12-01 |  | 378295178 | 5% | 54% | Ongoing
14 | Price variation for Mukuru MET Two Bedroom Units - call off 1 | Nairobi | Embakasi South | Social and Physical Infrastructure |  |  | 1 | 2025-12-01 | 2026-12-01 |  | 213895275 | 5% | 54% | Ongoing
15 | Price variation for Mukuru MET Two Bedroom Units - call off 2 | Nairobi | Embakasi South | Social and Physical Infrastructure |  |  | 1 | 2025-12-01 | 2026-12-01 |  | 179538992 | 5% | 54% | Ongoing
16 | Proposed completion works for Mukuru MET bedsitters call off 2 and 3 (21 No. blocks) | Nairobi | Embakasi South | Social and Physical Infrastructure |  |  | 1 | 2nd March 2026 | 2nd March 2027 |  | 664895076 | 98% | 29% | Ongoing
17 | Furnishing of social housing units for Mukuru Meteorological Site - Call off 1 Bedsitter units | Nairobi | Embakasi South | Social and Physical Infrastructure |  |  | - | TBD | TBD |  | 317520000 | 100% |  | Complete
18 | Hire of excavation equipment for bulk excavation at Meteorological Site (Earthmark Enterprises Limited) | Nairobi | Embakasi South | Social and Physical Infrastructure |  |  | 1 | 14th October 2020 | 13th November 2020 |  | 5689906 | 100% | 67% | This is interest amount due to delayed payment as resolved during arbitration settlement
19 | Proposed Procurement of LPG Fittings and Bulk Storage for 21 Blocks Of 4536 No. Units for Mukuru Social Housing | Nairobi | Embakasi South | Social Housing | Symetrics Limited | Linx Consulting Engineers Ltd. |  | 20th September 2025 | 20th July 2026 |  | 781051948 | 40% | 88% | Ongoing
20 | Proposed social Housing Units and associated social infrastructure at Kasarani Lot 1 | Nairobi | Kasarani | Social Housing | Concise Projects Ltd | Mutiso Menezes International Ltd | 2534 | 25th August 2025 | 25th August 2027 |  | 4093773374 | 3% | 40% | Ongoing
21 | Proposed social Housing Units and associated social infrastructure at Kasarani Lot 2 | Nairobi | Kasarani | Social Housing |  |  | 2534 | 7th August 2025 | 7th August 2027 |  | 4021000000 | 2% | 47% | Ongoing
22 | Proposed social Housing Units and associated social infrastructure at Kasarani Lot 3 | Nairobi | Kasarani | Social Housing | Sahjanad Construction Ltd | Dama Services Limited | 2353 | 14th September 2025 | 14th September 2027 |  | 3848988355 | 8% | 38% | Ongoing
23 | Proposed social Housing Units and associated social infrastructure at Kasarani Lot 4 | Nairobi | Kasarani | Social Housing | Double Portion Agency Limited | AAKI Consultants Limited | 2534 | 17th April 2025 | 17th April 2027 |  | 3979446842 | 8% | 72 | Ongoing
24 | Design, Build and Finance of Housing Units and associated Infrastructure for Kibera Soweto East Zone B. | Nairobi | Kibra | Social Housing |  |  | 4465 | 5th January 2023 | 4th January 2026 |  | 7458854144 | 82% | 115% | Ongoing
25 | Price variation of works for Kibera Soweto B project | Nairobi | Kibra | Social and Physical Infrastructure |  |  | 1 | 2025-12-01 | 2026-12-01 |  | 608826475 | 5% | 76% | Ongoing
26 | Proposed social Housing Units and associated social infrastructure at Kibra Lot 1 | Nairobi | Langata | Social Housing |  |  | 3000 | TBD | TBD |  | 4633000000 | 0% |  | Under procurement, project is to be transferred to KDF. Official communication pending hence monies not appropriated in the FYs
27 | Proposed social Housing Units and associated social infrastructure at Kibra Lot 2 | Nairobi | Langata | Social Housing | Shyam General Merchants | Design Artitude Limited | 2952 | 2025-03-01 | 2027-03-01 |  | 4853681525 | 2% | 65% | Ongoing
28 | Proposed social Housing Units and associated social infrastructure at Kibra Lot 3 | Nairobi | Langata | Social Housing |  |  | 2856 | 14th April 2025 | 14th April 2027 |  | 4835600990 | 5% | 59% | Ongoing
29 | Proposed social Housing Units and associated social infrastructure at Kibra Lot 4 | Nairobi | Langata | Social Housing |  |  | 2904 | 2025-03-01 | 2027-03-01 |  | 4781965299 | 2% | 66% | Ongoing
30 | Proposed social Housing Units and associated social infrastructure at Kibra Lot 5 | Nairobi | Langata | Social Housing |  |  | 3000 | 14th April 2025 | 14th April 2027 |  | 5041917102 | 2% | 59% | Ongoing
31 | Proposed social Housing Units and associated social infrastructure at Mathare 1 Lot 1 | Nairobi | Mathare | Social Housing | Nightigale (E.A) Limited | Cadplan Consultants Limited | 2672 | 5th May 2025 | 5th May 2027 |  | 4431330768 | 6% | 56% | Ongoing
32 | Proposed social Housing Units and associated social infrastructure at Mathare 2 Lot 2 | Nairobi | Mathare | Social Housing | Nightigale (E.A) Limited | Tej Architects | 2840 | 30th April 2025 | 30th April 2027 |  | 5335000000 | 5% | 56% | Ongoing
33 | Proposed construction and finance of SEPU AHP | Nairobi | Starehe | Social Housing |  |  | 4076 | TBD | TBD |  | 9304936166.37 | 1% |  | Ongoing
34 | Proposed social Housing Units and associated social infrastructure at Kamiti Lot 1 | Kiambu |  | Social Housing | Greenhill |  | 2325 | 6th August 2025 | 6th August 2027 |  | 4087000000 | 4% | 43% | Ongoing
35 | Proposed social Housing Units and associated social infrastructure at Kamiti Lot 2 | Kiambu | Kiambu Town | Social Housing | Double Portion Agency Ltd | Tectura International Limited | 1963 | 17th April 2025 | 17th April 2027 |  | 3177337857 | 37% | 58% | Ongoing
36 | Proposed Social Housing Units and associated civil works at Kibera Soweto Zone C & D Kibra Constituency, Nairobi County LOT 2 | Nairobi | Langata | Social Housing |  |  | TBD | TBD | TBD |  | 0 | 0% |  | Ongoing
37 | Proposed Social Housing Units and associated civil works at Kibera Soweto Zone C & D Kibra Constituency, Nairobi County LOT 3 | Nairobi | Langata | Social Housing |  |  | TBD | TBD | TBD |  | 0 | 0% |  | Ongoing
38 | Proposed Social Housing Units and associated civil works at Kibera Soweto Zone C & D Kibra Constituency, Nairobi County LOT 4 | Nairobi | Langata | Social Housing |  |  | TBD | TBD | TBD |  | 0 | 0% |  | Ongoing
39 | Proposed social Housing Units and associated social infrastructure at Mariguini, Nairobi County | Nairobi | Starehe | Social Housing | Parklane Construction Ltd & Masterpower Systems Ltd JV | AIA Architects Limited | 2304 | 19th May 2026 | 19th May 2028 |  | 4328976976 | 0% | 0% | Ongoing
| TOTAL FOR SOCIAL HOUSING | [5 empty] | 50672 |  |  |  | 81343457515 | 37.69%
SOCIAL INFRASTUCTURE
40 | Proposed Installation of. Solar powered high mast floodlights in Nairobi County | Nairobi | Kasarani | High Mast Floodlights | Safari Outsourcing and Network Solutions Limited |  | 3 | 18th October 2024 | 19th December 2025 |  | 19029240 | 20% | 143% | Ongoing Contractor to complete by end of August 2026
41 | Proposed Installation of. Solar powered high mast floodlights in Nairobi County | Nairobi | Dagoreti North | High Mast Floodlights | Safari Outsourcing and Network Solutions Limited |  | 1 | 18th October 2024 | 19th December 2025 |  | 6343080 | 46% | 247% | Ongoing Contractor to complete by end of August 2026
42 | Proposed Installation of. Solar powered high mast floodlights in Nairobi County | Nairobi | Embakasi West | High Mast Floodlights | Safari Outsourcing and Network Solutions Limited |  | 1 | 18th October 2024 | 19th December 2025 |  | 6343080 | 46% | 142% | Ongoing Contractor to complete by end of August 2026
43 | Proposed Installation of. Solar powered high mast floodlights in Nairobi County | Nairobi | Ruaraka | High Mast Floodlights | Safari Outsourcing and Network Solutions Limited |  | 1 | 18th October 2024 | 19th December 2025 |  | 6343080 | 20% | 138% | Ongoing Contractor to complete by end of August 2026
44 | Installation of 2No. Solar Powered High Mast Floodlights at Kawangware Day and Congo Roundabout in Dagoretti North Constituency, Nairobi | Nairobi | Dagoretti North | High Mast Floodlights | Shrewsbury Limited |  | 2 | 14th July 2025 | 29th December 2025 |  | 13121516 | 35% | 200% | Ongoing
45 | Proposed multipurpose hall and ablution block in Mathare 4B, Mathare Constituency, Nairobi County | Nairobi | Mathare | Social and Physical Infrastructure | Amis Relite LTD |  | 1 | TBD | TBD |  | 23040737.5 | 0% |  | Ongoing (Change of design)
46 | Proposed Njathani-Bustani Road in Roysambu Constituency, Nairobi County | Nairobi | Roysambu | Physical Infrastructure | Gadal Holdings Limited | TBC | 1 | 28th May 2026 | 28th November 2026 |  | 45786315.34 |  |  | 3 km
| TOTAL FOR SOCIAL INFRASTRUCTURE | [5 empty] | 9 |  |  |  | 74220733.5 | 27.83%
SOCIAL PROJECTS
47 | Nairobi River re- engineering | Nairobi | Various | Physical Infrastructure |  |  | 1 | 2024-07-01 | 2027-06-30 |  | 56000000000 | 30% | 49.8% | The scope of work was increased.
48 | Climate WorkX | Nairobi | Various | Social and Physical Infrastructure |  |  | 1 | 2025-07-01 | 2027-06-30 |  | 8506516926.85 | 38% | 32.7% | Ongoing
49 | Facilitation of relocation of PAPs for Mukuru, Kiambiu, Mariguini and Kibera informal settlements | Nairobi | Various | - |  |  | 1 | TBD | TBD |  | 850000000 | 100% |  | Complete
50 | Consultancy of Relocation Action Plan for Mukuru, Kiambiu, Mariguini and Kibera informal settlements | Nairobi | Various | Consultancy |  |  | 1 | 8th July 2025 | 30th December 2025 |  | 34832664 | 100% | 195% | Complete
| TOTAL FOR SOCIAL PROJECTS | [5 empty] | 4 |  |  |  | 65391349591 | 67%
| GRAND TOTAL FOR PROJECTS | [5 empty] | 50685 |  |  |  | 146809027840 | 44.38%

## WEST RIFT
S/No. | Project Name | County | Constituency | Project Type | Contractor | Consultant | No. of Units | Start Date | End Date | Revised End Date | Project Estimated Cost (KES) | Completion Status (%) | Time Lapsed( %) | Remarks | No. of Workers on Site | Latest Date Updated
MARKETS
38 | Construction of markets and supporting facilities in Kisii County- Egetuki | Kisii | Bomachoge Chache | Markets | Skillman Construction LTD |  | 1 | 15th July, 2024 | 6th March 2026 |  | 55197915 | 92% | 117% | Ongoing
39 | Construction of markets and supporting facilities in Kisii County- Masimba | Kisii | Nyaribari Masaba | Markets | Skillman Construction LTD |  | 1 | 14th July, 2024 | 6th March 2027 |  | 55197915 | 96% | 73% | Ongoing
57 | Proposed Construction of Kahawa Market in Nyamira County | Nyamira | North Mugirango | Market | Vibercom LTD |  | 1 | 3rd August 2022 | 18th July 2024 |  | 18192075 | 100% | 197% | Complete
| TOTAL FOR MARKETS | [5 empty] | 3 |  |  |  | 128587905 | 96%
SOCIAL INFRASTRUCTURE
82 | Proposed Installation of Solar powered high mast floodlights in Kisii County | Kisii | Nyaribari Masaba | High Mast Floodlights | Elymax Agencies Limited |  | 3 | 21st January 2025 | 7th December 2025 | 31st August 2026 | 19109686 | 75% | 159% | Ongoing
83 | Proposed Installation of Solar powered high mast floodlights in Kisii County | Kisii | Bobasi | High Mast Floodlights | Elymax Agencies Limited |  | 3 | 21st January 2025 | 7th December 2025 | 31st August 2026 | 19109686 | 75% | 159% | Ongoing
116 | Proposed Installation of Solar powered high mast floodlights in Nyamira County | Nyamira | Kitutu Masaba | High Mast Floodlights | Safari Outsourcing & Network Solutions Limited |  | 2 | 24th September 2024 | 5th December 2025 | 31st August 2026 | 14054402 | 75% | 144% | Ongoing
| TOTAL FOR SOCIAL INFRASTRUCTURE | [5 empty] | 8 |  |  |  | 52273774 | 75%
| GRAND TOTAL FOR PROJECTS | [5 empty] | 11 |  |  |  | 180861679 | 85.5%

## WESTERN
S/No. | Project Name | County | Constituency | Project Type | Contractor | Consultant | No. of Units | Start Date | End Date | Revised End Date | Project Estimated Cost (KES) | Completion Status (%) | Time Lapsed( %) | Remarks | No. of Workers on Site | Latest Date Updated
MARKETS
28 | Construction of markets and supporting facilities in Bungoma- Luandanyi | Bungoma | Sirisia | Markets | Contralinks Solutions & Services Limited | N/A | 1 | 5th October 2024 | 30th October 2025 |  | 49206561 | 79% | 337.5% | Contractor to fast track on works | 8 | 15/07/2026
29 | Construction of markets and supporting facilities in Busia- Amagoro | Busia | Teso North | Markets | Contralinks Solutions & Services Limited | N/A | 1 | 25th July 2024 | 30th October 2025 |  | 49206561 | 97% | 337.5% | Civil Works to Commence | 10 | 15/07/2026
35 | Construction of markets and supporting facilities in Kakamega- Muregu (Originally Navakholo) | Kakamega | Navakholo | Markets | Contralinks Solutions & Services Limited | N/A | 1 | 17th September 2024 | 30th October 2025 |  | 49206561 | 87% | 337.5% | Contractor to mobilise labour and fast track on works | 2 | 15/07/2026
| Construction of market shed and supporting infrastructure in Busia - Namboboto Market | Busia | Funyula | Market shed | Alljay Trans Limited | Dama Services | 1 | 7th April 2026 | 7th October 2026 |  | 23645025 | 3% | 58.3% | Contractor to resume works | 0 | 15/07/2026
| TOTAL FOR MARKETS | [5 empty] | 4 |  |  |  | 171264708 | 66.5%
SOCIAL INFRASTRUCTURE
60 | Proposed Installation of Solar powered high mast floodlights Busia County | Busia | Teso North | High Mast Floodlights | Safari outsourcing and network solutions |  | 2 | 23rd September 2024 | 10th March 2025 |  | 13977089 | 50% | 391.6% | Contractor to fast track works |  | 15/07/2026
68 | Proposed Installation of Solar powered high mast floodlights in Kakamega County | Kakamega | Lugari | High Mast Floodlights | Hyannis limited |  | 2 | 24th september 2025 | 11th March 2025 |  | 12780059 | 50% | 391.6% | Contractor to fast track works |  | 15/07/2026
| Installation of 3 2No. Solar Powered High mast Floodlights in Sirisia Constituency - Bungoma County | Bungoma | Sirirsia | High Mast Floodlights | Incate Company Limited |  | 3 | 13th February 2026 | 13th August 2026 |  | 24868287 | 3% | 87.5% | Works behind schedule. MC to fast track works |  | 15/7.2026
| TOTAL FOR SOCIAL INFRASTRUCTURE | [5 empty] | 7 |  |  |  | 51625435 | 34.33%
| GRAND TOTAL FOR PROJECTS | [5 empty] | 11 |  |  |  | 222890143 | 72.6%

## S.RIFT
SOUTH RIFT REGION
S/No. | Project Name | County | Constituency | Project Type | Location | Contractor | Contract No. | Consultant | No. of Units | Contract Period | Handover Date | Start Date | End Date | Practical Completion Date | Project Estimated Cost (KES) | Cumulative Payments to Date | Balance | Completion Status (%) | Time Lapsed( %) | Remarks | No. of Workers on Site | Latest Date Updated | Supplementary Info
SOCIAL HOUSING
1 | Proposed Construction of Social Housing Units and Associated Social Infrastructure at Michinda Boys Primary School, Molo Constituency, Nakuru County | Nakuru | Molo | Social Housing | Elburgon | Earthcare Services Limited | MLPWHUD/SDHUD/SUD/381/2023-2024 | Alphaquest Designs Consortium Ltd. | 2480 | 24 Months |  | 7th July 2025 | 7th July 2027 |  | 4223502375 | 765668110.2 | 3457834265 | 11% | 46% | Ongoing
| TOTAL FOR MARKETS | [7 empty] | 2480 | [5 empty] | 4223502375 |  |  | 11%
MARKETS
2 | Construction of markets and supporting facilities in Baringo County - Mogotio | Baringo | Mogotio | Markets |  | Manje Company Limited | MLPWHUD/SDHUD/SUD/255/2023-2024 |  | 1 | 6 Months |  | 26th April 2024 | 26th October 2024 |  | 49984570 | 46262091 | 3722479 | 100% | 424% | Complete |  |  | Market Capacity: 200
3 | Construction of markets and supporting facilities in Baringo County- Tenges | Baringo | Kabarnet Central | Markets |  | Manje Company Limited | MLPWHUD/SDHUD/SUD/255/2023-2024 |  | 1 | 6 Months |  | 26th April 2024 | 26th October 2024 |  | 49984570 | 11202873 | 38781697 | 10% | 424% | Ongoing. |  |  | Market Capacity: 200
4 | Construction of markets and supporting facilities in Bomet- Kapkwen | Bomet | Bomet Central | Markets |  | Tevene Enterprise Ltd | MLPWHUD/SDHUD/SUD/254/2023-2024 - Cluster 9 |  | 1 | 6 Months |  | 30th April 2024 | 30th October 2024 |  | 55163503 | 12517856 | 42645647 | 10% | 424% | Ongoing |  |  | Market Capacity: 200
5 | Construction of markets and supporting facilities in Bomet - Koiwa | Bomet | Konoin | Markets |  | Tevene Enterprise Ltd | MLPWHUD/SDHUD/SUD/254/2023-2024 - Cluster 9 |  | 1 | 6 Months |  | 8th May, 2024 | 23rd October 2024 |  | 55163503 | 22646986 | 32516517 | 14% | 455% | Ongoing |  |  | Market Capacity: 200
6 | Proposed Construction of markets and supporting facilities in Kericho- Lelu | Kericho | Kipkelion West | Markets |  | Tevene Enterprise Ltd | MLPWHUD/SDHUD/SUD/254/2023-2024 - Cluster 9 |  | 1 | 6 Months |  | 12th September, 2024 | 27th February, 2025 |  | 55163503 |  | 55163503 | 0% | 379% | Not commenced
7 | Proposed construction of Nakuru Multipurpose Market in Nakuru County | Nakuru | Nakuru Town East | Markets |  | Derow Construction Company Limited |  |  | 1 |  |  | 4th November 2020 | 4th November 2024 |  | 612502225 | 595677158 | 16825067 | 100% | 140% | 100% |  |  | Market Capacity: 200. Confirm for Final A/C
8 | Proposed Construction of Markets and Supporting Facilities in Nakuru - Kasarani | Nakuru | Subukia | Markets |  | Pecar Investment Limited | MLPWHUD/SDHUD/SUD/245/2023-2024 - Cluster 1 |  | 1 | 6 Months |  | 23rd July 2024 | 2nd January 2026 |  | 51146285.8 | 31703987 | 19442298.8 | 94% | 131% | Ongoing (Had variation of scope)
9 | Proposed Construction of Markets and Supporting Facilities in Nakuru - Dundori (Mutumba) | Nakuru | Bahati | Markets |  | Pecar Investment Limited | MLPWHUD/SDHUD/SUD/245/2023-2024 - Cluster 1 |  | 1 | 6 Months |  | 23rd July 2024 | 2nd January 2026 |  | 51146285.8 | 39845837 | 11300448.8 | 70% | 131% | Ongoing(Had variation of scope)
10 | Proposed Construction of Markets and Supporting Facilities in Nakuru County- Seguton | Nakuru | Kuresoi North | Markets |  | Flolizz Contractors Limited | MLPWHUD/SDHUD/SUD/258/2023-2024 CLUSTER 12 | Dama Services Limited | 1 | 6 Months |  | 26th August 2024 | 27th October 2025 |  | 50382335 | 25198785 | 25183550 | 65% | 153% | Ongoing
11 | Construction of markets and supporting facilities in Nakuru County- Kiptagich | Nakuru | Kuresoi South | Markets |  | Flolizz Contractors Limited | MLPWHUD/SDHUD/SUD/258/2023-2024 CLUSTER 12 | Dama Services Limited | 1 | 6 Months |  | 5th June 2024 | 27th October 2025 |  | 50382335 | 29795306 | 20587029 | 97% | 145% | Ongoing
12 | Construction of markets and supporting facilities in Nakuru County- Nyamamithi (Kiboronjo) | Nakuru | Rongai | Markets |  | Flolizz Contractors Limited | MLPWHUD/SDHUD/SUD/258/2023-2024 CLUSTER 12 | Dama Services Limited | 1 | 6 Months |  | 15th June 2024 | 27th October 2025 |  | 50382335 | 23666612 | 26715723 | 71% | 146% | Ongoing
13 | Construction of markets and supporting facilities in Narok County - Mamboleo | Narok | Emurua Dikkir | Markets |  | Samoha Construction limited/Luusha Investments Limited | MLPWHUD/SDHUD/SUD/249/2023-2024 (Cluster 5) |  | 1 | 6 Months |  | 29th April 2024 | 29th December, 2025 |  | 52606495 | 47363190 | 5243305 | 80% | 127% | Ongoing
14 | Construction of markets and supporting facilities in Narok County - Olchoro | Narok | Narok North | Markets |  | Samoha Construction limited/Luusha Investments Limited | MLPWHUD/SDHUD/SUD/249/2023-2024 (Cluster 5) |  | 1 | 6 Months |  | 28th May 2024 | 29th December, 2025 |  | 52606495 | 32757981 | 19848514 | 39% | 129% | Ongoing
| TOTAL FOR MARKETS | [7 empty] | 13 | [5 empty] | 1236614441 |  |  | 57.69%
SOCIAL INFRASTRUCTURE
15 | Proposed Installation of Solar powered high mast floodlights in Kericho County | Kericho | Sigor | High Mast Floodlights |  |  |  |  | 1 |  |  | TBD | TBD |  | 6609724 |  | 6609724 | 1% |  | site handover to contractor |  |  | Duplicate
16 | Proposed Installation of Solar powered high mast floodlights in Kericho County | Kericho | Chebunyo | High Mast Floodlights |  |  |  |  | 1 |  |  | TBD | TBD |  | 6609724 |  | 6609724 | 1% |  | site handover to contractor |  |  | Duplicate
17 | Installation of 2No. solar powered high mast flood lighting in Kipkelion East Constituency, Kericho County | Kericho | Kipkelion East | High Mast Floodlights |  |  |  |  | 2 |  |  | 8th April 2025 | 2nd January 2026 |  | 15870213 |  | 15870213 | 86% | 160% | Ongoing |  |  | Duplicated
15 | Proposed installation of 2.NO Electric powered high mast floodlighting structures in Timau and Subukia | Nakuru | Subukia | High Mast Floodlights |  | Yakuti Blue |  |  | 2 | 6 Months |  | 22nd February 2024 | 22nd May 2024 |  | 9572436 |  | 9572436 | 100% | 928% | Project complete |  |  | Confirm if relocated to Meru County
16 | Proposed Siberian Centre Installation of Solar powered high mast floodlights in Nakuru County (Proposed Installation of 16No. Solar-powered Highmast Floodlights in Bahati 3No., Subukia 3No., Molo 3No., Gilgil 3No. Elburgon 2No. and Kuresoi South 2No. - Nakuru County - Cluster 19) | Nakuru | Bahati | High Mast Floodlights | Bahati | Worcester Engineering Ltd | MLPWHUD/SDHUD/SUD/169/2023-2024 Cluster 19 |  | 3 | 24 Weeks |  | 9th September 2025 | 24th February 2026 |  | 18690784 | 1526245 | 17164539 | 35% | 165% | Ongoing ➢ Hand Over Date: MP DECLINED to handover Subukia Constituency Sites ➢ Contractor placed a request for these items in March 2025 to the Project Manager and is still awaiting feedback ➢ Contractor placed a request for these items in March 2025 to the Project Manager and is still awaiting feedback
17 | Proposed Siberian Centre Installation of Solar powered high mast floodlights in Nakuru County (Proposed Installation of 16No. Solar-powered Highmast Floodlights in Bahati 3No., Subukia 3No., Molo 3No., Gilgil 3No. Elburgon 2No. and Kuresoi South 2No. - Nakuru County - Cluster 19) | Nakuru | Subukia | High Mast Floodlights | Subukia | Worcester Engineering Ltd | MLPWHUD/SDHUD/SUD/169/2023-2024 Cluster 19 |  | 3 | 24 Weeks |  | 9th September 2025 | 24th February 2026 |  | 18690784 | 1526245 | 17164539 | 35% | 165%
18 | Proposed Siberian Centre Installation of Solar powered high mast floodlights in Nakuru County (Proposed Installation of 16No. Solar-powered Highmast Floodlights in Bahati 3No., Subukia 3No., Molo 3No., Gilgil 3No. Elburgon 2No. and Kuresoi South 2No. - Nakuru County - Cluster 19) | Nakuru | Kuresoi South | High Mast Floodlights | Kuresoi South | Worcester Engineering Ltd | MLPWHUD/SDHUD/SUD/169/2023-2024 Cluster 19 |  | 2 | 24 Weeks |  | 9th September 2025 | 24th February 2026 |  | 18690784 | 1526245 | 17164539 | 35% | 165%
19 | Proposed Siberian Centre Installation of Solar powered high mast floodlights in Nakuru County (Proposed Installation of 16No. Solar-powered Highmast Floodlights in Bahati 3No., Subukia 3No., Molo 3No., Gilgil 3No. Elburgon 2No. and Kuresoi South 2No. - Nakuru County - Cluster 19) | Nakuru | Molo | High Mast Floodlights | Keringet, Mukinyai, Molo Hospital | Worcester Engineering Ltd | MLPWHUD/SDHUD/SUD/169/2023-2024 Cluster 19 |  | 3 | 24 Weeks |  | 9th September 2025 | 24th February 2026 |  | 24921046 | 1526245 | 23394801 | 35% | 165%
20 | Proposed Siberian Centre Installation of Solar powered high mast floodlights in Nakuru County (Proposed Installation of 16No. Solar-powered Highmast Floodlights in Bahati 3No., Subukia 3No., Molo 3No., Gilgil 3No. Elburgon 2No. and Kuresoi South 2No. - Nakuru County - Cluster 19) | Nakuru | Molo | High Mast Floodlights | Elburgon | Worcester Engineering Ltd | MLPWHUD/SDHUD/SUD/169/2023-2024 Cluster 19 |  | 2 | 24 Weeks |  | 9th September 2025 | 24th February 2026 |  | 6230261 | 1526245 | 4704016 | 35% | 165%
21 | Proposed Siberian Centre Installation of Solar powered high mast floodlights in Nakuru County (Proposed Installation of 16No. Solar-powered Highmast Floodlights in Bahati 3No., Subukia 3No., Molo 3No., Gilgil 3No. Elburgon 2No. and Kuresoi South 2No. - Nakuru County - Cluster 19) | Nakuru | Gilgil | High Mast Floodlights | Royal Estate, Site Kanjo & Gema | Worcester Engineering Ltd | MLPWHUD/SDHUD/SUD/169/2023-2024 Cluster 19 |  | 3 | 24 Weeks |  | 9th September 2025 | 24th February 2026 |  | 12460523 | 1526245 | 10934278 | 35% | 165%
22 | Proposed Installation of 3No. Solar Powered High Mast Floodlights, NAROK COUNTY | Narok | Emurua Dikkir | High Mast Floodlights | Emurua Dikir | Elymax Agencies Limited | MLPWHUD/SDHUD/SUD/171/2023-2024 |  | 3 |  |  | 11th November 2024 | 28th April 2025 |  | 19109686 | 9634933 | 9474753 | 48% | 225% | ➢ Works awarded lacked critical items such as the battery housing, solar panel mounting structure,razor wire, electric fence and the gate. ➢ Contractor placed a request for these items in March 2025 to the Project Manager and is still awaiting feedback. |  |  | ➢ IPC Certified & Paid in March 2025 ➢ EOT Application sent to PM by contractor, awaiting processing
23 | Proposed Construction of Nakuru City Bus Park- Nakuru county | Nakuru | Nakuru East | Social and Physical Infrastructure |  | Rural Distributors Enterprise LTD | MTIHUDPW/SDHUD/SUD/UDD/47/2021-2022 |  | 1 |  |  | 3rd May 2022 | 29th October 2025 |  | 269375853 | 248295059.2 | 21080793.8 | 95% | 117% | Ongoing
24 | Proposed construction of a Boarding Facilities: Boys and Girls Dormitories, Kitchen, Dining Hall, Multi- purpose Hall and Ablution Blocks at Mlimani Primary School, Nakuru Town. | Nakuru | Nakuru Town West | Social and Physical Infrastructure |  |  |  |  | 1 |  |  | 20th July 2020 | 16th October 2024 |  | 145647060 |  | 145647060 | 100% | 138% | Complete
25 | Proposed construction of 10 No. classrooms at Limuko Primary School | Nakuru | Bahati | Social and Physical Infrastructure |  | Megapro Engineering Limited | MLPWHUD/SDHUD/SUD/260/2023-2024 |  | 1 | 12 Months |  | 7th March 2025 | 6th March 2026 |  | 49893884.25 | 28795575 | 21098309.25 | 89% | 127% | Ongoing
26 | Proposed Construction of 2No. Footbridge in Kuresoi North Constituency ,Nakuru | Nakuru | Kuresoi North | Social and Physical Infrastructure |  | Worcester Engineering Limited | MLPWHUD/SDHUD/SUD/194/2023-2024 |  | 2 | 26 Weeks |  | 31st Jan 2025 | 31st July 2025 |  | 14048221 |  | 14048221 | 100% | 276% | Complete |  |  | Yet
27 | Proposed Drilling , equipping of Borehole and erection of water tower at Simboyoni Primary, Subukia, Nakuru County | Nakuru | Subukia | Social and Physical Infrastructure |  | Pecar Investment Limited | MLPWHUD/SDHUD/SUD/179/2023-2024 |  | 1 | 24 Weeks |  | 24th June 2025 | 10th December 2025 |  | 11499312 | 10781318 | 717994 | 94% | 210% | Ongoing
28 | TOTAL FOR SOCIAL INFRASTRUCTURE | [7 empty] | 31 | [5 empty] | 647920295.3 |  | 64792029530% | 57.75%
29 | [16 empty] | 0
30 | GRAND TOTAL FOR PROJECTS | [7 empty] | 2524 | [5 empty] | 6108037111 |  | 6108037111 | 56.17%
31 | Proposed construction of Market and supporting facilities in Transmara West at Angata Bariko in Narok County |  | Narok | Angata Barikoi |  | Decree company limited | MLPWHUD/SDHUD/SUD/755/2024-2025 |  | 1 | 9 Months | 2026-03-17 | 2026-04-01 | 2027-01-02 |  | 66465738 | 11087072.9 | 55378665.1 | 27.66% | 43.3% | Ongoing |  |  | No ongoing market shed project done in this constituency by SUD. Capacity: 80 ¦ Delayed Payment
32 | Proposed Installation of 4No. solar powered high mast floodlights in Rafiki shopping centre (1No.), Kapnyangale centre(1No.), and East Gate (2No.) - Nakuru County |  | Nakuru | Various |  | Standard Heights Limited | MLPWHUD/SDHUD/SUD/766/204-2025 |  | 4 | 24 Weeks |  | 2026-06-01 | 2026-11-01 |  | 32617065.6 |  | 32617065.6 | 35.1% |  | Evaluation. Moved from Under Procurement/. Contract Updated from 32,000,000.00 |  |  | Construction of 1 No. ESP market at Rongai Construction of Nakuru Multi purpose market at Nakuru Town East No ongoing highmast project done in the two constituecies by SUD
33 | Proposed construction of Market and supporting facilities in Transmara East Njipishi in Narok County |  | Narok | Transmara East Njipishi |  | Alljay Trans Limited | MLPWHUD/SDHUD/SUD/754/2024-2025 |  | 1 | 6 Months |  | 2026-07-13 | 2027-01-13 |  | 23645025 |  | 23645025 | 0% |  | Moved from Under Procurement/. Contract sum Updated from 30,000,000.00 |  |  | No ongoing market shed project done in this constituency by SUD
34 | Proposed Installation of Solar powered high mast floodlights in Kericho County -Sigor | Bomet | Chepalungu | Sigor |  | Hyannis Limited |  |  | 1 | 24 Weeks |  | 2024-12-04 | 2025-06-04 |  | 6609724 | 3454844 | 3154880 | 48% | 212.5 | ➢ Works awarded lacked critical items such as the battery housing, solar panel mounting structure, razor wire, electric fence and the gate. ➢ Contractor placed a request for these items in March 2025 to the Project Manager and is still awaiting feedback. |  | 0
35 | Proposed Installation of Solar powered high mast floodlights in Kericho County - Chebunyo Town | Bomet | Chepalungu | Chebunyo |  | Hyannis Limited |  |  | 1 | 24 Weeks |  | 2024-12-04 | 2025-06-04 |  | 6609724 | 3454844 | 3154880 | 48% | 212.5 |  |  | 0
36 | Proposed Installation of 2 No. Solar Powered Highmast Floodlighting in Kipkelion East Constituency, Kericho County | Kericho | Kipkelion East | Kipkelion East | Londiani & Chepseon Centres | Hamethyst Limited |  |  | 2 |  | 2025-03-25 | 2025-04-08 | 2025-09-23 |  | 15870213.25 |  | 15870213.25 | 100% |  | Practical Complete |  | 0 | Final A/C Paid paid
37 | Installation of 2No. solar powered floodlight in Toroton Centre and Kacheliba Centre in Kipkelion West constituency,Kericho County | Kericho | Kipkelion West | Kipkelion West |  | Yakuti Blue Limited In JV with Powernet |  |  | 2 |  |  | 2026-02-21 | 2026-08-21 |  | 15937359.48 |  | 15937359.48 |  |  | Ongoing

## N.RIFT
S/No. | Project Name | Contract No. | County | Constituency | Project Type | Contractor | Consultant | No. of Units | Start Date | End Date | Revised End date | Project Estimated Cost (KES) | Completion Status (%) | Time Lapsed( %) | Remarks | No. of Workers on Site | Latest Date Updated
MARKETS
1 | Construction of markets and supporting facilities in Elgeyo Marakwet - Iten | MLPWHUD/SDHUD/SUD/247/2023-2024. | Elgeyo Marakwet | Keiyo South | Markets | Marc Construction Works Limited |  | 1 | 9th April 2024 | 13th October 2025 |  | 54549090 | 100% | 144% | Complete
2 | Construction of markets and supporting facilities in Uasin Gishu - Matharu | MLPWHUD/SDHUD/SUD/247/2023-2024. | Uasin Gishu | Kesses | Markets | Marc Construction Works Limited |  | 1 | 9th April 2024 | 13th October 2025 |  | 54549090 | 100% | 144% | Complete
| TOTAL FOR MARKETS | [6 empty] | 2 |  |  |  | 109098180 | 100%
SOCIAL INFRASTRUCTURE
3 | Proposed Installation of. Solar powered high mast floodlights in Nandi County | MLPWHUD/SDHUD/SUD/170/2023-2024 | Nandi | Mosop | High Mast Floodlights | Tyngsborough Limited |  | 3 | 7th December 2024 | 31st May 2025 |  | 19075245 | 40% | 208.3% | ➢ Works awarded lacked critical items such as the battery housing, solar panel mounting structure, razor wire, electric fence and the gate which was later approved. ➢Ongoing
4 | Proposed Installation of. Solar powered high mast floodlights in Nandi County | MLPWHUD/SDHUD/SUD/170/2023-2024 | Nandi | Chesumei | High Mast Floodlights | Tyngsborough Limited |  | 2 | 7th December 2024 | 31st May2025 |  | 12716830 | 40% | 208.3% | ➢ Works awarded lacked critical items such as the battery housing, solar panel mounting structure, razor wire, electric fence and the gate which was later approved. ➢Ongoing
5 | Installation of 2No. solar powered high mast flood lighting in Emgwen Constituency, Nandi County | MLPWHUD/SDHUD/SUD/359/2023-2024 | Nandi | Emgwen | High Mast Floodlights | Contralinks Solutions & Services Limited |  | 2 | 21st March 2025 | 2nd January 2026 |  | 15907217 | 100% | 157% | Complete
6 | Proposed Installation of Solar powered high mast floodlights in Trans Nzoia County | MLPWHUD/SDHUD/SUD/175/2023-2024 | Trans Nzoia | Kiminini | High Mast Floodlights | Tyngsborough Limited |  | 3 | 10th March 2025 | 25th August 2025 |  | 19075245 | 48% | 154.2% | ➢Works awarded lacked critical items such as the battery housing, solar panel mounting structure, razor wire, electric fence and the gate which was later approved. ➢Ongoing
7 | Proposed Installation of 1No. Solar powered high mast floodlight in Kipkeikei, Trans Nzoia County | MLPWHUD/SDHUD/SUD/365/2023-2024 | Trans Nzoia | Cherangany | High Mast Floodlights | Stan holdings Company Limited |  | 1 | 23rd March 2025 | 8th September 2025 |  | 7925856 | 100% | 145.8% | Complete
8 | Proposed Installation of Solar powered high mast floodlight, Uasin Gishu County |  | Uasin Gishu | Moiben | High Mast Floodlights |  |  | 1 | TBD | TBD |  | 6300000 | 0% |  | Under procurement
9 | Proposed Installation of Solar powered high mast floodlight, Uasin Gishu County |  | Uasin Gishu | Kapseret | High Mast Floodlights |  |  | 1 | TBD | TBD |  | 6300000 | 0% |  | Under procurement
| TOTAL FOR SOCIAL INFRASTRUCTURE | [6 empty] | 13 |  |  |  | 87300393 | 46.86%
| GRAND TOTAL FOR PROJECTS | [6 empty] | 15 |  |  |  | 196398573 | 58.67%

## NYANZA
| Project Name | County | Constituency | Project Type | Contractor | Consultant | No. of Units | Start Date | End Date | Revised End Date | Project Estimated Cost (KES) | Completion Status (%) | Time Lapsed( %) | Remarks | No. of Workers on Site | Latest Date Updated
MARKETS
1 | Construction of markets and supporting facilities in Homabay County- Kobodo | Homabay | Ndhiwa | Markets | Chridal Enterprises Limited |  | 1 | 15th June 2024 | 19th January 2026 |  | 48501760 | 100% | 80% | complete
2 | Construction of markets and supporting facilities in Homabay County- Kijebi | Homabay | Suba South | Markets | Chridal Enterprises Limited |  | 1 | 15th June, 2024 | 19th January 2026 |  | 48501760 | 100% | 80% | complete
3 | Construction of markets and supporting facilities in Migori County- Rapogi Oria Uriri | Migori | Uriri | Markets | Chridal Enterprises Limited |  | 1 | 15th July, 2024 | 25th December, 2024 |  | 47501065 | 99% | 72% | Ongoing
4 | Construction of markets and supporting facilities in Migori County- Nyakweri | Migori | Nyatike | Markets | Chridal Enterprises Limited |  | 1 | 2nd January, 2025 | 2nd July, 2025 |  | 47501065 | 77% | 64% | Ongoing; had challenges with land
5 | Proposed construction of market and supporting facilities at Bonde Migori County- Kojea | Migori | Rongo | Markets | Karura Engineering Works Ltd |  | 1 | 15th April 2025 | 15th October 2025 |  | 14613407.03 | 75% | 217% | Ongoing; site moved to Kojea
6 | Proposed construction of market shed and supporting facilities at Oyani Maasai Migori County- Moved to Benga | Migori | Awendo | Markets | Vemash Investments Limited |  | 1 | 20th December 2025 | 8th October 2026 |  | 15955379 | 48% | 250% | Notice of site abandonmemnt issued to the contractor no substantial or valid request for Extension of Time (EOT) has been submitted in accordance with the Contract requirements
7 | Proposed construction of market and supporting facilities at Piny Oyie Migori County | Migori | Suna West | Markets | Vemash Investments Limited |  | 1 | 20th December, 2024 | 20nd June, 2025 |  | 15955379 | 70% | 250%
8 | Construction of 1No. market and supporting facilities at Obambo, in Alego Usonga, Siaya County - To be moved to Ting Wangi | Siaya | Alego Usonga | Markets | Stima Networks Limited |  | 1 | 12th December 2025 | 12th June 2026 |  | 24238130.5 | 5% | 90% | Ongoing
| TOTAL FOR MARKETS | [5 empty] | 8 |  |  |  | 238529815 | 81.29%
PHYSICAL INFRASTRUCTURE
9 | Proposed Installation of Solar powered high mast floodlights in Homabay County | Homabay | Suba South | High Mast Floodlights | Hamethyst Limited |  | 2 | 26th March 2025 | 24th December 2025 |  | 15888715 | 100% | 61% | Complete
10 | Installation of 2 No. solar powered high mast flood lighting in Kabondo Kasipul, Kabondo Kasipul Constituency, Homabay County | Homabay | Kabondo Kasipul | High Mast Floodlights | Stan Holdings Company Limited |  | 2 | 17th March 2025 | 30th March 2025 |  | 16400000 | 100% | 3% | Complete
11 | Installation of 2No. Solar Powered High Mast Floodlights in Suba South Constituency, Homabay County | Homabay | Suba South | High Mast Floodlights | Safari Outsourcing and Network Solutions Limited |  | 2 | 24th September 2024 | 11th March 2025 |  | 13849489 | 75% |  | Ongoing
12 | Installation of 2No. solar powered high mast flood lighting in Homa Bay Town Constituency, Homabay County | Homabay | Homabay Town | High Mast Floodlights | Hamethyst Limited |  | 2 | 13th March 2025 | 30th March 2026 |  | 15888715 | 100% |  | Complete
13 | Installation of 2No. solar powered high mast flood lighting in Suba North Constituency, Homabay County | Homabay | Suba North | High Mast Floodlights | Hamethyst Limited |  | 2 | 15th March 2025 | 30th March 2026 |  | 15888715 | 100% | 83% | Complete
14 | Proposed Installation of. Solar powered high mast floodlights in Migori County | Migori | Suna West | High Mast Floodlights | Safari Outsourcing and Network Solutions Ltd |  | 2 | 24th September 2024 | 11th March 2025 |  | 14192210 | 50% | 27% | Ongoing project stalled , contractor cites delayed ipc pending
15 | Installation of 2 No. solar powered high mast flood lighting in Awendo Constituency, Migori County | Migori | Awendo | High Mast Floodlights | Contralinks Solutions and Services Limited |  | 2 | 26th March 2025 | 12th December 2025 |  | 15907217 | 100% | 59% | Project complete
16 | Installation of 2No. solar powered high mast flood lighting in Kuria East Constituency, Migori County | Migori | Kuria East | High Mast Floodlights | Contralinks Solutions and Services Limited |  | 2 | 28th March 2025 | 15th December 2025 |  | 15907217 | 100% | 59% | Project complete
17 | Proposed Installation of Solar powered high mast floodlights in Siaya County | Siaya | Ugenya | High Mast Floodlights | Safari Outsourcing and Network Solutions Limited |  | 2 | 2nd October 2024 | 19th March 2025 |  | 13990602 | 50% | 27% | Ongoing
18 | Installation of 2No. solar powered high mast flood lighting at Gagra Market and Asembo Bay market in Rarieda Constituency Siaya County | Siaya | Rarieda | High Mast Floodlights | Hamethyst Limited |  | 2 | 21st February 2025 | 24th December 2025 |  | 15888715 | 100% | 64% | Complete
19 | Proposed Installation of 3No. Solar Powered High Mast Floodlighting in Various Centres in Rongo Constituency, Migori County | Migori | Rongo | High Mast Floodlights | Seaways Centre Investment Limited |  | 3 | 13th August 2025 | 31st July 2026 |  | 20869203.04 | 98% |  | Ongoing. IPC 1 Submitted 16,806,748 Final snagging ongoing"
| TOTAL FOR SOCIAL INFRASTRUCTURE | [5 empty] | 23 |  |  |  | 153801595 | 87.5%
| GRAND TOTAL FOR PROJECTS | [5 empty] | 25 |  |  |  | 392331410 | 84.94%

## COAST & N.EASTERN
S/No. | Project Name | County | Constituency | Project Type | Contractor | Consultant | No. of Units | Start Date | End Date | Revised End Date | Project Estimated Cost (KES) | Completion Status (%) | Time Lapsed( %) | Remarks | No. of Workers on Site | Latest Date Updated
MARKETS
41 | Proposed construction of Hagdera Modern Market and supporting Facilities in Hagdera Costituency, Garissa County | Garissa | Hagdera | Markets | M/S Selfie Construction and Suppliers Limited |  | 1 |  |  |  | 192429603.87 |  |  | Awaiting Site Handover
42 | Proposed Renovation of Market Sheds in Lafey, Mandera county | Mandera | Lafey | Markets |  |  | 1 | 15th June 2022 | 24th June 2024 |  | 17004858 | 85% | 202.4% | Ongoing
| TOTAL FOR MARKETS | [5 empty] | 2 |  |  |  | 209434461.9 | 85% | 202.4%
SOCIAL INFRASTRUCTURE
81 | Proposed Installation of Solar powered high mast floodlights in Kilifi County | Kilifi | Kilifi North | High Mast Floodlights | Elymax | Slum Upgrading Department | 2 | 12th November 2024 | 25th May 2025 |  | 12739791 | 60% | 318% | Ongoing
89 | Proposed Installation of Solar powered high mast floodlights, Lamu County | Lamu | Lamu West | High Mast Floodlights | Safari Outsourcing Limited | slum Upgrading Department (SUD) | 2 | 26th June 2024 | 28th December 2024 |  | 14472930 | 90% | 408.6% | Ongoing
93 | Proposed Installation of Solar powered high mast floodlights, Mandera | Mandera | Lafey | High Mast Floodlights | Tyngsborough Limited | Slum Upgrading Department(SUD | 2 | 8th April 2025 | 8th November 2025 |  | 14007121 | 75% | 390.2% | Ongoing
122 | Installation of 2No. high mast flood lighting in Buura Constituency, Tana River County | Tana River | Bura | High Mast Floodlights | Contralinks Solutions and Services Limited | Slum Upgrading Department (SUD) | 2 | 28th April 2025 | 29th October 2025 |  | 16400000 | 100% |  | Complete
128 | Installation of Solar powered high mast floodlights, Wajir County | Wajir | Wajir East | High Mast Floodlights | safari Outsourcin & Network solution Limited | Slum Upgrading Department(SUD | 2 | 3Oth May 2025 | 30th November 2025 |  | 14093830 | 20% | 227.2% | ongoing
129 | Installation of 150No. solar street lights in Watamu, Kilifi North Constituency, Kilifi County | Kilifi | Kilifi North | Highmast | solarcom | Slum Upgrading Department(SUD) | 1 | 8th August 2025 | 6th February 2026 |  | 37500000 | 100% | 200% | complete
133 | Proposed Construction of Changamwe Youth Centre in Mombasa County | Mombasa | Changamwe | Social and Physical Infrastructure |  |  | 1 | 21st December 2024 | 21st June 2025 |  | 58585529 | 100% | 316.7% | Complete
| Installation Of 4 No. Solar Powered High Mast Floodlights In Kariakoo Central Village, Ikanga Shopping Centre, Maweni Village And Mwalangi Shopping Centre, Voi Constituency –Taita Taveta County. | Taita Taveta | Various | High Mast Floodlights | M/S Viva Creative Agency Limited. | Slum Upgrading Department | 4 | 29th May 2026 | 29th November 2026 |  | 34449181.2 |  | 33.33%
| Proposed Installation Of 1 No. Solar Powered High Mast Flood Lights In Kamtonga Trading Centre Mwatate Constituency –Taita Taveta County. | Taita Taveta | Mwatate | High Mast Floodlights | M/S Viva Creative Agency Limited. | Slum Upgrading Department | 1 | 29th May 2026 | 29th November 2026 |  | 8612295.3 |  | 33.33%
| Installation Of 1 No. Solar Powered High Mast Flood Lights In Kariobangi Mwatate Constituency –Taita Taveta County. | Taita Taveta | Mwatate | High Mast Floodlights | Sharp Industries Limited. | Slum Upgrading Department | 1 | 3oth April 2026 | 30th October 2026 |  | 8289429.08 |  | 50%
| TOTAL FOR SOCIAL INFRASTRUCTURE | [5 empty] | 12 |  |  |  | 167799201 | 77.86%
| GRAND TOTAL FOR PROJECTS | [5 empty] | 14 |  |  |  | 377233662.9 | 78.75%

## NAIROBI METRO
| Project Name | County | Constituency | Project Type | Contractor | Consultant | No. of Units | Start Date | End Date | Revised End date | Project Estimated Cost (KES) | Completion Status (%) | Time Lapsed( %) | Remarks | No. of Workers on Site | Latest Date Updated
MARKETS
| Construction of markets and supporting facilities in Kajiado County- Mashuru | Kajiado | Kajiado East | Markets | Start General contractors |  | 1 | 6th May, 2024 | 6th May 2025 |  | 105946996 | 90.39% | 201.9% | Ongoing
34 | Construction of markets and supporting facilities in Kajiado County- Saikeri | Kajiado | Kajiado West | Markets | Start General contractors |  | 1 | 19th July 2024 | 19th July 2025 |  | 105946996 | 89.5% | 201.9% | Ongoing
37 | Construction of markets and supporting facilities in Kiambu -Kahuho | Kiambu | Kabete | Markets | Pecar Investment Ltd |  | 1 | 6th March 2025 | 6th September, 2025 |  | 52276746.16 | 93% | 263.6% | Ongoing
| TOTAL FOR MARKETS | [5 empty] | 3 |  |  |  | 264170738.2 | 90.96%
PHYSICAL INFRASTUCTURE
74 | Installation of 2No. solar powered high mast flood lighting in Gatundu North Constituency, Kiambu County | Kiambu | Gatundu North | High Mast Floodlights | Stan Holding ltd |  | 2 | 3rd February 2025 | 4th August 2025 |  | 15728302 | 100% | 272% | Complete
75 | Proposed Installation of. Solar powered high mast floodlights in Kiambu County | Kiambu | Thika Town | High Mast Floodlights | Universal Trends ltd |  | 2 | 19th July 2024 | 19th February 2026 |  | 15356830 | 40% | 119% | Ongoing
76 | Proposed Installation of. Solar powered high mast floodlights in Kiambu County | Kiambu | Kiambaa | High Mast Floodlights | Universal Trends ltd |  | 2 | 19th July 2024 | 19th February 2026 |  | 15356830 | 40% | 119% | Ongoing
77 | Proposed Installation of. Solar powered high mast floodlights in Kiambu County | Kiambu | Kabete | High Mast Floodlights | Universal Trends ltd |  | 2 | 19th July 2024 | 19th February 2026 |  | 15356830 | 40% | 119% | Ongoing
78 | Proposed Installation of. Solar powered high mast floodlights in Kiambu County | Kiambu | Ruiru | High Mast Floodlights | Universal Trends ltd |  | 3 | 19th July 2024 | 19th February 2026 |  | 23035243 | 40% | 119% | Ongoing
79 | Installation of 2No. Solar Powered High Mast Floodlights at Ngoingwa Thika west and Munyu Thika East in Thika town Constituency, Kiambu | Kiambu | Thika Town | High Mast Floodlights | Stan Holding ltd |  | 2 | 26th February 2025 | 27th August 2025 |  | 15728302 | 100% | 259% | Complete
80 | Installation of 3No. solar powered high mast flood lighting in Ruiru Constituency, Kiambu County | Kiambu | Ruiru | High Mast Floodlights | Universal Trends ltd |  | 3 | 19th March 2025 | 19th September 2025 |  | 24600000 | 40% | 245% | Ongoing
90 | Proposed 2No. Installation of Solar powered high mast floodlights in Machakos County Kathemboni and Kameo | Machakos | Machakos Town | High Mast Floodlights | Stan Holdings Company Limited |  | 2 | 10th February 2025 | 10th August 2025 |  | 15753393 | 100% | 269% | Complete
130 | Proposed Construction of Dining Hall and Dormitory at Alliance High School Kiambu County | Kiambu | Kikuyu | Social and Physical Infrastructure |  |  | 1 | 29th April 2024 | 28th April 2025 |  | 279596803 | 95% | 213% | Ongoing
132 | Access road to Ndenderu Market upgrade to Cabro (Kiambaa Constituency - Kiambu County | Kiambu | Kiambaa | Social and physical infrastructure | M/S KAKIDAKI AGENCIES LTD |  | 1 | 9th February 2026 | 9th August 2026 |  | 17262957.6 | 99% | 69% | Complete
145 | Price variation for Construction of Dining Hall and Dormitory at Alliance High School Kiambu County | Kiambu | Kikuyu | Social and Physical Infrastructure |  |  | 1 | 2025-12-01 | 2026-12-01 |  | 68817709 | 1% |  | Ongoing
167 | Proposed Access and Upgrading to Carbro of Thimbigua Primary School in Kiambaa, Kiambu County | Kiambu | Kiambaa | Physical Infrastructure | Transgenic Solution Limited | TBC |  | TBD | TBD |  | 24996222.3 |  |  | Not yet started as at 14-Jul-2026
178 | Proposed upgrading to cabro standards of access roads - Karuri market access roads - Karuri market access road and Kihara modern market access road in Kiambaa Constituency, Kiambu County | Kiambu | Kiambaa | Social and Physical Infrastructure | Grandways Company Limited |  | 1 | TBD | TBD |  | 61795839 | 85% |  | Contracted. Moved from Under Procurement . Progress as at 27th April | No ongoing access road project done in this constituency by SUD Installation of 2No. highmasts ongoing
| TOTAL FOR SOCIAL INFRASTRUCTURE | [5 empty] | 21 |  |  |  | 506593199.6 | 63.18%
| GRAND TOTAL FOR PROJECTS | [5 empty] | #REF! |  |  |  | #REF! | 63.06%

## EASTERN
S/No. | Project Name | County | Constituency | Project Type | Contractor | Consultant | No. of Units | Start Date | End Date | Revised End Date | Project Estimated Cost (KES) | Completion Status (%) | Time Lapsed( %) | Remarks | No. of Workers on Site | Latest Date Updated
MARKETS
41 | Construction of market and supporting facilities in Makueni County- Mutulani | Makueni | Kaiti | Markets | Workhose Holding Limited |  | 1 | 19th October 2024 | 19th October 2025 | 31st July 2026 | 54368777 | 85% | 173 | Ongoing |  | 28th July,2026
| TOTAL FOR MARKETS | [5 empty] | 1 |  |  |  | 54368777 | 85%
SOCIAL INFRASTRUCTURE
62 | Proposed Installation of Solar powered high mast floodlights in Manyatta Embu County | Embu | Manyatta | High Mast Floodlights | Safari Outsoourcing and Network Solutions Limited |  | 3 | 27th June 2024 | 20th November 2024 | . | 20774234 | 80% | 511 | contractor abandoned site |  | 28th July,2026
91 | Proposed Installation of Solar powered high mast floodlights, Makueni County | Makueni | Kaiti | High Mast Floodlights | M/S/ Hyannis Limited |  | 3 | 4th September,2024 | 12th April,2025 | . | 20471719 | 20% | 308 | Ongoing |  | 28th July,2026
92 | Proposed Installation of Solar powered high mast floodlights, Makueni County | Makueni | Kibwezi West | High Mast Floodlights | M/S Hyannis Limited |  | 2 | 4th September,2024 | 12th April,2025 |  | 13647813 | 20% | 308 | Ongoing |  | 28th July,2026
94 | Proposed installation of 2.NO Electric powered high mast floodlighting structures in Timau and Subukia | Meru | Buuri | High Mast Floodlights | M/S Yakuti Blue Limited |  | 2 | 22nd February 2024 | 22nd May 2024 |  | 9572436 | 100% | 970 | Complete |  | 28th July,2026
96 | Proposed Installation of 5 no. Solar powered high mast floodlights in Meru County | Meru | North Imenti | High Mast Floodlights | Wrochester Engineering LTD |  | 5 | 16th September 2024 | 3rd March 2025 | 31st July 2026 | 31151307 | 45% | 396 | Site handed over to contractor |  | 28th July,2026
123 | Installation of 3No. Solar powered high mast at Mukothima, Gatunga and Kibung'a Markets in Tharaka Constituency, Tharaka Nithi County | Tharaka Nithi | Tharaka | High Mast Floodlights | M/S Hypertech Electrical Services Limited |  | 3 | 2025-06-01 | 2025-12-01 |  | 24600000 | 0% |  | Site handed over to contractor. no show |  | 28th July,2026
131 | Proposed Water reticulation in Timau informal settlement Phase 2 | Meru | Buuri | Social and Physical Infrastructure | Anamic ventures LTD |  | 1 | 26th March 2025 | 31st July 2026 |  | 21815388 | 20% | 91 | Ongoing |  | 28th July,2026
| TOTAL FOR SOCIAL INFRASTRUCTURE | [5 empty] | 19 |  |  |  | 142032897 | 40.71%
41 | Installation of 1No. 20m high solar powered floodlights in Mwichiune market, South Imenti constituency, Meru County | Meru | South Imenti | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
42 | Installation of 1No. 20m high solar powered floodlight in Shauri Yako Informal Settlement, Meru County | Meru | Imenti North | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | Advertised
87 | Installation of 1No. 20m high solar powered floodlights in Njukiri, Manyatta constituency, Embu County | Embu | Manyatta | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
92 | Installation of 1No. 20m high solar powered floodlight in Isiolo North Constituency, Isiolo County | Isiolo | Isiolo North | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
93 | Installation of 1No. 20m high solar powered floodlight in Isiolo South Constituency, Isiolo County | Isiolo | Isiolo South | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
109 | installation of 1No. 20m high solar powered flood lights at Kyatune market in Kitui South Constituency. | Kitui | Kitui South | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
110 | Installation of 1No. 20m high solar powered flood lights at Mitinyani Market in Kitui West Constituency, Kitui County | Kitui | Kitui West | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
111 | Installation of 1No 20m high solar powered highmast flood lighting structures in Mwingi Town | Kitui | Mwingi North | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
112 | Installation of 1No. 20m high solar powered flood lights at Migwani Market in Mwingi West Constituency, Kitui County | Kitui | Mwingi West | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
127 | Installation of 1No. 20m high solar powered floodlight in Musalala market in Kaiti Constituency,Makueni County | Makueni | Kaiti | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
128 | Installation of 1No. 20m high solar powered floodlight in Ulilinzi shopping centres in Kibwezi East Constituency,Makueni County | Makueni | Kibwezi East | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
129 | Installation of 1No. 20m high solar powered floodlight in Kikumini in Kibwezi West Constituency,Makueni County | Makueni | Kibwezi West | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
130 | Installation of 1No. 20m high solar powered floodlight in Nzeveni in Kilome Constituency,Makueni County | Makueni | Kilome | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
131 | Installation of 1No. 20m high solar powered floodlight in Kwa Mutula in Makueni Constituency,Makueni County | Makueni | Makueni | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
132 | Installation of 1No. 20m high solar powered floodlight in Watuka market in Mbooni Constituency,Makueni County | Makueni | Mbooni | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
171 | Installation of 1No. 20m high solar powered floodlight in Kajuki market, Chuka Igamba Ngombe constituency,Tharaka Nithi County | Tharaka Nithi | Chuka Igamba Ngombe | Highmast |  |  | 1 | TBD | TBD | 5000000 | 0% | In EGP awaiting requisition
195 | Proposed construction of completion works at Nchaure Primary, North Imenti Constituency in Meru county | Meru | North Imenti | Social and Physical Infrastructure |  |  | 1 | TBD | TBD | 10000000 | 0% | In EGP awaiting tendering
| GRAND TOTAL FOR PROJECTS | [5 empty] | 20 |  |  |  | 196401674 | 46.25%

## CENTRAL
| Project Name | County | Constituency | Project Type | Contractor | Consultant | No. of Units | Start Date | End Date | Revised End Date | Project Estimated Cost (KES) | Completion Status (%) | Time Lapsed( %) | Remarks | No. of Workers on Site | Latest Date Updated
MARKETS
1 | Construction of market and supporting facilities in Laikipia County- Ilipolei | Laikipia | Laikipia North | Markets | Masterprice Suppliers Limited |  | 1 | 7th July 2024 | 7th January 2025 |  | 57291801 | 43.6% | 437.5% | Ongoing |  | 29/07/2026
2 | Construction of markets and supporting facilities in Murang'a- Karugia | Muranga | Kangema | Markets | Pecar Investment Limited |  | 1 | 30th May 2024 | 16th January 2026 |  | 52993396 | 97% | 445.8% | Ongoing |  | 29/07/2027
3 | Construction of markets and supporting facilities in Nyandarua- Ol Kalau (Mirangine) | Nyandarua | Ol Kalou | Markets | Pecar Investment Limited |  | 1 | 23rd July 2024 | 2nd January 2026 |  | 51812952 | 95.89% | 354.3% | Ongoing |  | 29/07/2028
| TOTAL FOR MARKETS | [5 empty] | 3 |  |  |  | 162098149 | 78.83%
SOCIAL INFRASTRUCTURE
4 | Proposed 2no. Installation of. Solar powered high mast floodlights in Laikipia County | Laikipia | Laikipia West | High Mast Floodlights | Universal Trends |  | 2 | 27th June 2024 | 20th November 2024 |  | 12001710 | 5% | 20% | Ongoing |  | 29/07/2026
5 | Proposed 2no. Installation of. Solar powered high mast floodlights in Laikipia County | Laikipia | Laikipia East | High Mast Floodlights | Universal Trends |  | 1 | 27th June 2024 | 20th November 2024 |  | 6000855 | 5% | 20% | Ongoing |  | 29/07/2027
6 | Proposed Installation of. Solar powered high mast floodlights in Laikipia County | Laikipia | Laikipia North | High Mast Floodlights | Universal Trends |  | 1 | 27th June 2024 | 20th November 2024 |  | 6000855 | 5% | 20% | Ongoing |  | 29/07/2028
7 | Installation of 2No. solar powered high mast flood lighting in Oljororook Constituency, Laikipia County | Laikipia | Oljororok | High Mast Floodlights | Seaways Centre Investment Limited |  | 2 | 18th March 2025 | 29th December 2025 |  | 14872290 | 100% | 100% | Complete |  | 29/07/2029
8 | Proposed Installation of Solar powered high mast floodlights in Nyandarua County | Nyandarua | Kipipiri | High Mast Floodlights |  |  | 2 | 27th June 2024 | 20th November 2024 |  | 13221147 | 5% | 20% | Ongoing |  | 29/07/2030
9 | Proposed Installation of Solar powered high mast floodlights in Nyandarua County | Nyandarua | Ol Kalou | High Mast Floodlights |  |  | 2 | 27th June 2024 | 20th November 2024 |  | 13221147 | 5% | 20% | Stalled |  | 29/07/2031
10 | Proposed construction of Tuition block and associated works at Githura Primary School, Nyeri County | Nyeri | Kieni | Social and Physical Infrastructure | KaxparTechnical Works Ltd |  | 1 | 6th January 2025 | 8th November 2025 |  | 51960133 | 85% | 58% | Ongoing |  | 29/07/2032
11 | Additional works for Githura Primary school | Nyeri | Kieni | Social and Physical Infrastructure | KaxparTechnical Works Ltd |  | 1 | 2025-12-01 | 2026-12-01 |  | 12800000 | 5% | 66% | Ongoing |  | 29/07/2033
12 | Proposed construction of Laboratory Ablution block and incinerator at Unjiru Health Center Nyeri County | Nyeri | Mathira | Social and Physical Infrastructure | Buona Agencies |  | 1 | 13th September 2022 | 14th February 2026 |  | 37412224 | 100% | 1 | Complete |  | 29/07/2034
13 | Construction of Cabro Works at Gakuwre Market, Murang'a County | Murang'a | Kiharu | Access Road | Hibonds Limited |  | 1 | 24th April 2026 | 24th October 2026 |  | 83998639.2 | 15% | 38% | Ongoing |  | 29/07/2035
14 | Proposed Upgrading to Bituminous Standards of Mukuyu Market Soko ya Mbuzi Access Road, Murang'a County | Murang'a | Kiharu | Access Road | Grandways Company Limited |  | 1 | 24th April 2026 | 24th October 2026 |  | 71496600 | 15.42% | 50.52% | Ongoing |  | 29/07/2036
15 | Proposed Upgrading to Cabro Standards of Mukuyu Market Access Road in Kiharu Constituency, Murang'a County | Murang'a | Kiharu | Access Road | Ochean Bays Investment Limited |  | 1 | 23rd April 2026 | 23rd October 2026 |  | 52974352 | 30% | 50.5% | Ongoing |  | 29/07/2037
| TOTAL FOR SOCIAL INFRASTRUCTURE | [5 empty] | 16 |  |  |  | 375959952.2 | 35%
| GRAND TOTAL FOR PROJECTS | [5 empty] | 16 |  |  |  | 538058101.2 | 45.96%