MINISTRY OF LANDS, PUBLIC WORKS, HOUSING AND URBAN DEVELOPMENT

STATE DEPARTMENT OF HOUSING AND URBAN DEVELOPMENT

SLUM UPGRADING DEPARTMENT

MEMO

To	: 	Principal Secretary

Through:     Ag. Secretary, IPDU/PMO

From	: 	Director, Slum Upgrading Department

Ref	: 	MLPWHUD/HUD/SUD/9/12/12 (30)

Date	: 	12th May, 2026

PAYMENT CONSENT: M/S FLOLIZZ CONTRACTORS LIMITED

PROPOSED CONSTRUCTION OF ESP MARKETS AND SUPPORTING FACILITIES IN NAKURU COUNTY- CLUSTER 12.

CONTRACT NO: MLPWHUD/SDHUD/SUD/258/2023-2024.

The above project is due for Interim Payment Certificate No. 06 as requested by the Contractor amounting to Kshs. 28,947,974.00 as per the tabulation below:

| Lot Procurement No.: | MLPWHUD/SDHUD/SUD/258/2023-2024. |
| --- | --- |
| Location | Nakuru County |
| Scope of Works: | Proposed Construction of ESP Markets and Supporting Facilities in Nakuru County |
| Employer: | Ministry of Lands, Public Works, Housing, and Urban Development |
| Implementing Authority: | Slum Upgrading Department (SUD) |
| Source of Funds: | G.O. K |
| Supervision Consultants: | Dama Services Limited |
| Contractor(s): | Flolizz Contractors Limited P.O. Box 1888-00200, Nairobi |
| Contract Sum: | Kshs 151,147,005.00 |
| Date Awarded: | February 25th 2024 |
| Date of Acceptance: | March 13th 2024 |
| Performance Guarantee: | SMEP Microfinance Bank, Nairobi Issued on March, 3rd 2026 Expires on September, 27th 2026 |
| Contractor’s All Risk Insurance: | Mayfair Insurance Co. Ltd Issued on 25th March 2026 Expires on 24th March 2027 |
| WIBA | Mayfair Insurance Co. Ltd Issued on 25th March 2026 Expires on 24th March 2027 |
| Tax compliance | Issued on August 6th 2025 Expires on August 5th 2026 |
| Valid NCA Registration Certificate | Issued on June 10th 2025 Expires on July 31st 2028 |
| Valid NCA practicing licence | Issued on June 10th 2025 Expires on July 31st 2026 |
| Bank Account Information: | Bank Name: Equity Bank Branch: Community Corporate Branch code: 68 Acc No.: 0240297266762 |
| Date of Signing Contract Agreement: | April 29th 2024 |
| Commencement Date: | Kiptagich Market- June 15th 2024 Nyamamithi Market- June 19th 2024 Seguton Market- August 26th 2024 |
| Date of Initial Completion: | Kiptagich Market- November 15th 2024 Nyamamithi Market- December 17th 2024 Seguton Market- 26th February 2025 |
| Status: | The proposed construction of the Markets, Kiptagich, Nyamamithi and Seguton ESP market, is still ongoing |
| Extension of time granted: | Interim Extension of time granted for the three ESP Markets up to July 31st 2026 |
| Revised: Completion Date: | July 31st 2026 |
| Period of Time Elapsed: | Kiptagich market- 93 weeks Nyamamithi Market- 91 weeks Seguton Market-82 weeks |
| Original Contract period | 6 Months |
| Percentage of Time Elapsed: | Kiptagich market- 430% Nyamamithi Market- 356.80% Seguton Market- 318.8% |
| Average Percentage of Permanent Work Complete: | Kiptagich market- 97.08% Nyamamithi Market- 70.7% Seguton Market- 65% Average: 77.59% |
| Percentage programmed |  |
| Defects Liability Period (D.L.P): |  |
| Start of Defects Liability Period: |  |
| Works Hand Over Date (End of D.L.P): |  |
| Variation Orders: | None |
| Claims: | None |
| Interest on Delayed Payments: | None |
| Liquidated Damages: | None |
| Advance Granted | Kshs 0.00 |
| Advance recovered |  |
| Advance Payment Guarantee: | None |
| Amount Paid to Date: | Kshs. 106,239,374.00 |
| This Certificate: | Kshs 28,947,974.00 |
| Total Cumulative Payments: | Kshs. 135,187,348.00 (89.44%) |
| Balance: | Kshs. 15,959,657.00 |
| Remarks (Challenges): | Power supply interruptions causing work interruptions. The discrepancy between the percentage of work done and the amount certified is due to variations encountered. The financial appraisals are pending approval. |

The purpose of this memo is to brief you on the current status for your information and approval of payment.

Mary W. Ndungu, OGW

Director, Slum Upgrading Department

Encls.